## Sheet1
SL. NO. | HELPER | PO DATE | PO NO. | SO. NO. | SITE ID | ZDM | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | VENDOR' NAME | STATUS | SITE ALLOTTED BY | COMPLETION DATE | JMR STATUS
1 | 46883¦KWL01 | 19.04.2018 | 46883 |  | KWL01 | Rahul Gupta | UEGT11970 | Lko Nsc | CIVIL(1.2X1.2), EW, BB & MH | Pawan Pratap Singh | 9935985000
2 | 47023¦GTN01 | 25.4.2018 | 47023 |  | GTN01 | Rahul Gupta | UEGT11597 | Lakhimpur | MW | Mukesh Kumar Mishra | 8052056483 | VIKASH SHUKLA | 36-280
3 | 47471¦ARJ01 | 15.05.2018 | 47471 | SO697099 | ARJ01 | Shambhu Nath | UEGT11119 | Deoria | CIVIL (1.2X1.2),EW & MH | GoPal Mishra | 9935599812 | NOOR AHMAD | PAD DONE ONLY |  | 10.06.2018 | JMR PREPARED FOR CIVIL & MH
4 | 47469¦DBH01 | 15.05.2018 | 47469 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | 3 EPM & MW IP55 | Shantosh Singh | 9628507454 | 35-120,220,310
5 | 47602¦DFP01 | 21.05.2018 | 47602 |  | DFP01 | Rahul Gupta | UEGT11875 | Sitapur | EW | Dileep Kumar | 9839661597
6 | 47653¦Construction of New Gorakhpur Zonal Office | 24.05.2018 | 47653 |  | Construction of New Gorakhpur Zonal Office | Shambhu Nath | #N/A | #N/A | Construction of New Gorakhpur Zonal Office | #N/A | #N/A
7 | 47671¦DBH01 | 23.05.2018 | 47671 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | CIVIL (1.2X1.2),EW & MH | Shantosh Singh | 9628507454
8 | 47671¦LKGP18 | 23.05.2018 | 47671 |  | LKGP18 | Rahul Gupta | UEGT10521 | Lko Nsc | EW | Imran Khan | 9795281428
9 | 47671¦NGP01 | 23.05.2018 | 47671 | SO685394 | NGP01 | Shambhu Nath | UEGT11257 | Deoria | EW | Sanjog Ku.Singh | 8052267418
11 | 47642¦KHD01 | 23.05.2018 | 47642 |  | KHD01 | Shambhu Nath | UEGT10345 | Basti | O&M EB Maintenance | Anoop Kumar Dubey | 9795301440 |  | HOLD
12 | 47735¦HSW01 | 28.05.2018 | 47735 |  | HSW01 | Shambhu Nath | UEGT11076 | Gorakhpur | DISM. OF SMPS & PIU | Dharmendra Pandey | 9956133918
13 | 47743¦MAL01 | 28.05.2018 | 47743 |  | MAL01 | Rahul Gupta | UEGT10545 | Lko Nsc | CIVIL (1.2X1.2),EW,2EPM,LADDER & PENDULUM | Sujeet Kumar Singh | 9936996735 | EPM DONE ONLY
14 | 47916¦PTI01 | 02.06.2018 | 47916 |  | PTI01 | Rahul Gupta | UEGT11666 | Lakhimpur | 3 EPM,MW IP55 & EW | Mohd. Shahid Khan | 7081990896 | SATYA PRAKASH | BB & ip 55DONE |  | 15.06.2018
15 | 47916¦GLK01 | 02.06.2018 | 47916 | SO680093 | GLK01 | Rahul Gupta | UEGT10978 | Sitapur | 3 EPM,MW IP55 & EW | Amit Singh | 9936966940 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 35-50,140,250
16 | 47916¦ENG01 | 02.06.2018 | 47916 | SO705974 | ENG01 | Rahul Gupta | UEGT12301 | Sitapur | 3 EPM,MW IP55 & EW | Pawan Kumar Mishra | 9956493163 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 38-1,120,260
17 | 48016¦LKSH10 | 07.06.2018 | 48016 |  | LKSH10 | Rahul Gupta | UEGT10497 | Shahjahanpur | MW | Raghuveer Singh Yadav | 9792469268 | VIKASH SHUKLA | MATERIAL NOR AVAILABLE | 38-334
18 | 47916¦SAL01 | 02.06.2018 | 47916 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | 3 EPM,MW IP55 & EW | Ram Lakhan | 9621911073 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 29-100,200,270
19 | 48016¦LKVN03 | 07.06.2018 | 48016 |  | LKVN03 | Rahul Gupta | UEGT10138 | Lko Nsc | MW | Ran Vijay Singh | 9621827562 | RAMESH
20 | 48071¦GPY01 | 11.06.2018 | 48071 |  | GPY01 | Rahul Gupta | UEGT12298 | Lakhimpur | EW | Harvansh Mani Tripathi | 9565065366
21 | 48130¦BNV01 | 14.06.2018 | 48130 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | EW | Mohd. Shahid Khan | 7081990896
22 | 48184¦LUK06 | 15.06.2014 | 48184 |  | LUK06 | Rahul Gupta | UERT10193 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Mangla Prasad | 8738888044
23 | 48184¦LUK05 | 15.06.2014 | 48184 |  | LUK05 | Rahul Gupta | UERT10053 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Dhirendra Pratap Singh | 9794704349
24 | 48184¦LUK112 | 15.06.2014 | 48184 |  | LUK112 | Rahul Gupta | UERT10856 | Lko Scn | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Ashutosh Kumar | 7607094484/9794999531
25 | 48186¦BNV01 | 15.06.2014 | 48186 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | BB | Mohd. Shahid Khan | 7081990896
26 | 48222¦LMP02 | 18.06.2014 | 48222 |  | LMP02 | Rahul Gupta | UEGT10567 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 | VIKASH SHUKLA | 38-307
27 | 48222¦KHR01 | 18.06.2014 | 48222 |  | KHR01 | Rahul Gupta | UEGT10662 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 | VIKASH SHUKLA | 35-58
28 | 48222¦BXS01 | 18.06.2014 | 48222 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | 2MW | Ram Lakhan | 9621911073
29 | 48222¦KAC01 | 18.06.2014 | 48222 |  | KAC01 | Rahul Gupta | UEGT10976 | Sitapur | 2MW | Ram Lakhan | 9621911073
30 | 48222¦MWQ01 | 18.06.2014 | 48222 |  | MWQ01 | Rahul Gupta | UEGT13091 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735
31 | 48222¦HZD01 | 18.06.2014 | 48222 |  | HZD01 | Rahul Gupta | UEGT13024 | Lakhimpur | 3EPM | Mohd. Shahid Khan | 7081990896 | VIKASH SHUKLA | 35-40,150,290
32 | 48222¦MJA01 | 18.06.2014 | 48222 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EPM | Harvansh Mani Tripathi | 9565065366 | VIKASH SHUKLA
33 | 48222¦CDP01 | 18.06.2014 | 48222 |  | CDP01 | Rahul Gupta | UEGT12149 | Lakhimpur | EPM | Upendra Kumar Dixit | 9839212570 | VIKASH SHUKLA
34 | 48222¦KME01 | 18.06.2014 | 48222 |  | KME01 | Rahul Gupta | UEGT11664 | Lko Nsc | EPM | Ran Vijay Singh | 9621827562
35 | 48222¦SAL01 | 18.06.2014 | 48222 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | EPM | Ram Lakhan | 9621911073
36 | 48222¦JSK01 | 18.06.2014 | 48222 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | 2EPM | Ran Vijay Singh | 9621827562
37 | 48333¦SEW01 | 21.06.2018 | 48333 |  | SEW01 | Shambhu Nath | UEGT10740 | Kushi Nagar | CIVIL (1.2X1.2),LADDER,PENDULUM,EPM,MW IP55,EW & MH | Ramesh ku. Gaur | 9838106014 | DEEPAK SINGH | PAD EXIST & T/RACK, EW DONE |  | 05.06.2018
38 | 48333¦BHO01 | 21.06.2018 | 48333 |  | BHO01 | Shambhu Nath | UEGT11778 | Mau | MW | Ashok Kumar Vishwkarma | 9839316559
39 | 48333¦GKVN11 | 21.06.2018 | 48333 |  | GKVN11 | Shambhu Nath | UEGT10257 | Mau | MW | Akhilesh Singh | 9936639664
40 | 48333¦KPB01 | 21.06.2018 | 48333 |  | KPB01 | Shambhu Nath | UEGT12560 | Deoria | EPM | Sher Bahadur Singh | 8948600632
41 | 48333¦SSY01 | 21.06.2018 | 48333 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | EPM | Sher Bahadur Singh | 8948600632
42 | 48333¦KZG01 | 21.06.2018 | 48333 |  | KZG01 | Shambhu Nath | UEGT13139 | Mau | EPM | Sanjay Kumar Singh | 9648887413
43 | 48351¦SSY01 | 22.06.2018 | 48351 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | BB | Sher Bahadur Singh | 8948600632
44 | 48351¦PGH01 | 22.06.2018 | 48351 |  | PGH01 | Shambhu Nath | UEGT11709 | Kushi Nagar | BB | Ramesh ku. Gaur | 9838106014 |  | DONE
45 | 48351¦SRH01 | 22.06.2018 | 48351 |  | SRH01 | Shambhu Nath | UEGT11338 | Maharajganj | BB | Harendra Kumar Patel | 9198673400 |  | DONE
46 | 48351¦GKP41 | 22.06.2018 | 48351 |  | GKP41 | Shambhu Nath | UERT10770 | Gorakhpur | BB | Dharmendra Pandey | 9956133918
47 | 48351¦DBH01 | 22.06.2018 | 48351 |  | DBH01 | Shambhu Nath | UEGT12186 | Mau | BB | Shantosh Singh | 9628507454
48 | 48380¦CHS01 | 25.06.2018 | 48380 |  | CHS01 | Shambhu Nath | UEGT11752 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014
49 | 48380¦SWM01 | 25.06.2018 | 48380 |  | SWM01 | Shambhu Nath | UEGT12742 | Mau | EW & BB | Amit Kumar Srivastava | 8115563289
50 | 48380¦SZR01 | 25.06.2018 | 48380 |  | SZR01 | Shambhu Nath | UEGT13279 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014
51 | 48380¦BIO01 | 25.06.2018 | 48380 |  | BIO01 | Shambhu Nath | UEGT12009 | Kushi Nagar | EW & BB | Susheel Kumar | 9198010591
52 | 48380¦DBD01 | 25.06.2018 | 48380 |  | DBD01 | Shambhu Nath | UEGT12470 | Basti | EW & BB | Arun Kumar TriPathi | 9984543050
53 | 48529¦ADD01 | 02.07.2018 | 48529 |  | ADD01 | Shambhu Nath | UEGT13176 | Mau | MW | Dhanjay Verma | 9795431482
54 | 48529¦MMK01 | 02.07.2018 | 48529 |  | MMK01 | Rahul Gupta | UEGT11654 | Sitapur | MW | Vivek Singh | 9648010660
55 | 48529¦SHA03 | 02.07.2018 | 48529 |  | SHA03 | Rahul Gupta | UEGT10273 | Shahjahanpur | 2MW | OM Prakash Singh | 9919901002
56 | 48529¦GMQ01 | 02.07.2018 | 48529 |  | GMQ01 | Rahul Gupta | UEGT13044 | Sitapur | MW | Vivek Singh | 9648010660
57 | 48529¦LKSH03 | 02.07.2018 | 48529 |  | LKSH03 | Rahul Gupta | UEGT10121 | Sitapur | MW | Ratish Dev Shukla | 9956167332
58 | 48529¦LKSH01 | 02.07.2018 | 48529 |  | LKSH01 | Rahul Gupta | UEGT10086 | Sitapur | MW | Ratish Dev Shukla | 9956167332
59 | 48529¦LAH01 | 02.07.2018 | 48529 |  | LAH01 | Rahul Gupta | UEGT10608 | Sitapur | MW | Surya Prakash Singh | 9956901615
60 | 48529¦DMR01 | 02.07.2018 | 48529 |  | DMR01 | Shambhu Nath | UEGT10615 | Basti | MW | Surendra Kumar Tripathi | 9792992998
61 | 48529¦CHP01 | 02.07.2018 | 48529 |  | CHP01 | Rahul Gupta | UEGT12226 | Sitapur | 2MW | Vivek Singh | 9648010660
62 | 48529¦BXS01 | 02.07.2018 | 48529 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | MW | Ram Lakhan | 9621911073
63 | 48529¦KZU01 | 02.07.2018 | 48529 |  | KZU01 | Rahul Gupta | UEGT11741 | Sitapur | 2MW | Ram Lakhan | 9621911073
64 | 48529¦KDZ01 | 02.07.2018 | 48529 |  | KDZ01 | Rahul Gupta | UEGT13356 | Shahjahanpur | 3MW | Praveen Kumar Yadav | 9721611872
65 | 48529¦STP05 | 02.07.2018 | 48529 |  | STP05 | Rahul Gupta | UEGT10891 | Sitapur | 2MW | Ram Lakhan | 9621911073
66 | 48529¦BET01 | 02.07.2018 | 48529 |  | BET01 | Shambhu Nath | UEGT12437 | Gorakhpur | 2MW | Satya Prakash Singh | 7317503030
67 | 48529¦BGZ01 | 02.07.2018 | 48529 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735
68 | 48572¦BPO01 | 03.07.2018 | 48572 |  | BPO01 | Rahul Gupta | UEGT12206 | Lakhimpur | MW | Shakeel Mirza | 8009937140
69 | 48572¦LKSH08 | 03.07.2018 | 48572 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | MW | Manik Chandra | 7080861480
70 | 48572¦GDE01 | 03.07.2018 | 48572 |  | GDE01 | Rahul Gupta | UEGT11089 | Sitapur | 2MW | Vivek Singh | 9648010660
71 | 48572¦ADH01 | 03.07.2018 | 48572 |  | ADH01 | Rahul Gupta | UEGT11652 | Lko Nsc | MW | Shiv Shankar | 9936028884
72 | 48572¦JTH01 | 03.07.2018 | 48572 |  | JTH01 | Rahul Gupta | UEGT12390 | Lakhimpur | MW | Sunil Kumar Gupta | 9984999462
73 | 48572¦REU01 | 03.07.2018 | 48572 |  | REU01 | Rahul Gupta | UEGT10985 | Sitapur | MW | Amit Singh | 9936966940