## ALLOCATION SHEET
SL. NO. | HELPER | PO DATE | PO NO. | SO. NO. | SITE ID | ZDM | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | VENDOR' NAME | STATUS | SITE ALLOTTED BY | COMPLETION DATE | JMR STATUS
1 | 46883¦KWL01 | 19.04.2018 | 46883 |  | KWL01 | Rahul Gupta | UEGT11970 | Lko Nsc | CIVIL(1.2X1.2), EW, BB & MH | Pawan Pratap Singh | 9935985000 | [5 empty] | LTS/1819/0646
3 | 47471¦ARJ01 | 15.05.2018 | 47471 | SO697099 | ARJ01 | Shambhu Nath | UEGT11119 | Deoria | CIVIL (1.2X1.2),EW & MH | GoPal Mishra | 9935599812 | NOOR AHMAD | PAD DONE ONLY |  | 10.06.2018 | JMR PREPARED FOR CIVIL & MH | #N/A
4 | 47469¦DBH01 | 15.05.2018 | 47469 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | 3 EPM & MW IP55 | Shantosh Singh | 9628507454 |  | 35-120,220,310 |  |  |  | #N/A
5 | 47602¦DFP01 | 21.05.2018 | 47602 |  | DFP01 | Rahul Gupta | UEGT11875 | Sitapur | EW | Dileep Kumar | 9839661597 | [5 empty] | #N/A
6 | 47653¦Construction of New Gorakhpur Zonal Office | 24.05.2018 | 47653 |  | Construction of New Gorakhpur Zonal Office | Shambhu Nath | #N/A | #N/A | Construction of New Gorakhpur Zonal Office | #N/A | #N/A | [5 empty] | #N/A
7 | 47671¦DBH01 | 23.05.2018 | 47671 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | CIVIL (1.2X1.2),EW & MH | Shantosh Singh | 9628507454 | [5 empty] | #N/A
8 | 47671¦LKGP18 | 23.05.2018 | 47671 |  | LKGP18 | Rahul Gupta | UEGT10521 | Lko Nsc | EW | Imran Khan | 9795281428 | [5 empty] | #N/A
9 | 47671¦NGP01 | 23.05.2018 | 47671 | SO685394 | NGP01 | Shambhu Nath | UEGT11257 | Deoria | EW | Sanjog Ku.Singh | 8052267418 | [5 empty] | #N/A
11 | 47642¦KHD01 | 23.05.2018 | 47642 |  | KHD01 | Shambhu Nath | UEGT10345 | Basti | O&M EB Maintenance | Anoop Kumar Dubey | 9795301440 |  | HOLD |  |  |  | #N/A
12 | 47735¦HSW01 | 28.05.2018 | 47735 |  | HSW01 | Shambhu Nath | UEGT11076 | Gorakhpur | DISM. OF SMPS & PIU | Dharmendra Pandey | 9956133918 | [5 empty] | #N/A
13 | 47743¦MAL01 | 28.05.2018 | 47743 |  | MAL01 | Rahul Gupta | UEGT10545 | Lko Nsc | CIVIL (1.2X1.2),EW,2EPM,LADDER & PENDULUM | Sujeet Kumar Singh | 9936996735 | VIKASH SHUKLA | DCDB & EPM DONE ONLY |  |  |  | #N/A
14 | 47916¦PTI01 | 02.06.2018 | 47916 |  | PTI01 | Rahul Gupta | UEGT11666 | Lakhimpur | 3 EPM,MW IP55 & EW | Mohd. Shahid Khan | 7081990896 | SATYA PRAKASH | BB & ip 55DONE |  | 15.06.2018 |  | #N/A
15 | 47916¦GLK01 | 02.06.2018 | 47916 | SO680093 | GLK01 | Rahul Gupta | UEGT10978 | Sitapur | 3 EPM,MW IP55 & EW | Amit Singh | 9936966940 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 35-50,140,250 |  |  | #N/A
16 | 47916¦ENG01 | 02.06.2018 | 47916 | SO705974 | ENG01 | Rahul Gupta | UEGT12301 | Sitapur | 3 EPM,MW IP55 & EW | Pawan Kumar Mishra | 9956493163 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 38-1,120,260 |  |  | #N/A
17 | 48016¦LKSH10 | 07.06.2018 | 48016 |  | LKSH10 | Rahul Gupta | UEGT10497 | Shahjahanpur | MW | Raghuveer Singh Yadav | 9792469268 |  | MATERIAL NOT AVAILABLE | 38-334 |  |  | #N/A
18 | 47916¦SAL01 | 02.06.2018 | 47916 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | 3 EPM,MW IP55 & EW | Ram Lakhan | 9621911073 | VIKASH SHUKLA | IP 55 DONE ONLY FULL MATERIAL NOT AVAILABLE | 29-100,200,270 |  |  | #N/A
19 | 48016¦LKVN03 | 07.06.2018 | 48016 |  | LKVN03 | Rahul Gupta | UEGT10138 | Lko Nsc | MW | Ran Vijay Singh | 9621827562 | [5 empty] | #N/A
20 | 48071¦GPY01 | 11.06.2018 | 48071 |  | GPY01 | Rahul Gupta | UEGT12298 | Lakhimpur | EW | Harvansh Mani Tripathi | 9565065366 | [5 empty] | #N/A
21 | 48130¦BNV01 | 14.06.2018 | 48130 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | EW | Mohd. Shahid Khan | 7081990896 | [5 empty] | #N/A
22 | 48184¦LUK06 | 15.06.2014 | 48184 |  | LUK06 | Rahul Gupta | UERT10193 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Mangla Prasad | 8738888044
23 | 48184¦LUK05 | 15.06.2014 | 48184 |  | LUK05 | Rahul Gupta | UERT10053 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Dhirendra Pratap Singh | 9794704349
24 | 48184¦LUK112 | 15.06.2014 | 48184 |  | LUK112 | Rahul Gupta | UERT10856 | Lko Scn | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Ashutosh Kumar | 7607094484/9794999531
25 | 48186¦BNV01 | 15.06.2014 | 48186 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | BB | Mohd. Shahid Khan | 7081990896
26 | 48222¦LMP02 | 18.06.2014 | 48222 |  | LMP02 | Rahul Gupta | UEGT10567 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 |  | 38-307
27 | 48222¦KHR01 | 18.06.2014 | 48222 |  | KHR01 | Rahul Gupta | UEGT10662 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 |  | 35-58
28 | 48222¦BXS01 | 18.06.2014 | 48222 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | 2MW | Ram Lakhan | 9621911073
29 | 48222¦KAC01 | 18.06.2014 | 48222 |  | KAC01 | Rahul Gupta | UEGT10976 | Sitapur | 2MW | Ram Lakhan | 9621911073
30 | 48222¦MWQ01 | 18.06.2014 | 48222 |  | MWQ01 | Rahul Gupta | UEGT13091 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735 | VIKASH SHUKLA
31 | 48222¦HZD01 | 18.06.2014 | 48222 |  | HZD01 | Rahul Gupta | UEGT13024 | Lakhimpur | 3EPM | Mohd. Shahid Khan | 7081990896 |  | 35-40,150,290
32 | 48222¦MJA01 | 18.06.2014 | 48222 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EPM | Harvansh Mani Tripathi | 9565065366
33 | 48222¦CDP01 | 18.06.2014 | 48222 |  | CDP01 | Rahul Gupta | UEGT12149 | Lakhimpur | EPM | Upendra Kumar Dixit | 9839212570
35 | 48222¦SAL01 | 18.06.2014 | 48222 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | EPM | Ram Lakhan | 9621911073
37 | 48333¦SEW01 | 21.06.2018 | 48333 |  | SEW01 | Shambhu Nath | UEGT10740 | Kushi Nagar | CIVIL (1.2X1.2),LADDER,PENDULUM,EPM,MW IP55,EW & MH | Ramesh ku. Gaur | 9838106014 | DEEPAK SINGH | PAD EXIST & T/RACK, EW DONE |  | 05.06.2018
38 | 48333¦BHO01 | 21.06.2018 | 48333 |  | BHO01 | Shambhu Nath | UEGT11778 | Mau | MW | Ashok Kumar Vishwkarma | 9839316559
39 | 48333¦GKVN11 | 21.06.2018 | 48333 |  | GKVN11 | Shambhu Nath | UEGT10257 | Mau | MW | Akhilesh Singh | 9936639664
40 | 48333¦KPB01 | 21.06.2018 | 48333 |  | KPB01 | Shambhu Nath | UEGT12560 | Deoria | EPM | Sher Bahadur Singh | 8948600632
41 | 48333¦SSY01 | 21.06.2018 | 48333 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | EPM | Sher Bahadur Singh | 8948600632
42 | 48333¦KZG01 | 21.06.2018 | 48333 |  | KZG01 | Shambhu Nath | UEGT13139 | Mau | EPM | Sanjay Kumar Singh | 9648887413
43 | 48351¦SSY01 | 22.06.2018 | 48351 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | BB | Sher Bahadur Singh | 8948600632
44 | 48351¦PGH01 | 22.06.2018 | 48351 |  | PGH01 | Shambhu Nath | UEGT11709 | Kushi Nagar | BB | Ramesh ku. Gaur | 9838106014 |  | DONE
45 | 48351¦SRH01 | 22.06.2018 | 48351 |  | SRH01 | Shambhu Nath | UEGT11338 | Maharajganj | BB | Harendra Kumar Patel | 9198673400 |  | DONE
46 | 48351¦GKP41 | 22.06.2018 | 48351 |  | GKP41 | Shambhu Nath | UERT10770 | Gorakhpur | BB | Dharmendra Pandey | 9956133918
47 | 48351¦DBH01 | 22.06.2018 | 48351 |  | DBH01 | Shambhu Nath | UEGT12186 | Mau | BB | Shantosh Singh | 9628507454
48 | 48380¦CHS01 | 25.06.2018 | 48380 |  | CHS01 | Shambhu Nath | UEGT11752 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014
49 | 48380¦SWM01 | 25.06.2018 | 48380 |  | SWM01 | Shambhu Nath | UEGT12742 | Mau | EW & BB | Amit Kumar Srivastava | 8115563289
50 | 48380¦SZR01 | 25.06.2018 | 48380 |  | SZR01 | Shambhu Nath | UEGT13279 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014
51 | 48380¦BIO01 | 25.06.2018 | 48380 |  | BIO01 | Shambhu Nath | UEGT12009 | Kushi Nagar | EW & BB | Susheel Kumar | 9198010591
52 | 48380¦DBD01 | 25.06.2018 | 48380 |  | DBD01 | Shambhu Nath | UEGT12470 | Basti | EW & BB | Arun Kumar TriPathi | 9984543050
53 | 48529¦ADD01 | 02.07.2018 | 48529 |  | ADD01 | Shambhu Nath | UEGT13176 | Mau | MW | Dhanjay Verma | 9795431482
55 | 48529¦SHA03 | 02.07.2018 | 48529 |  | SHA03 | Rahul Gupta | UEGT10273 | Shahjahanpur | 2MW | OM Prakash Singh | 9919901002
57 | 48529¦LKSH03 | 02.07.2018 | 48529 |  | LKSH03 | Rahul Gupta | UEGT10121 | Sitapur | MW | Ratish Dev Shukla | 9956167332
58 | 48529¦LKSH01 | 02.07.2018 | 48529 |  | LKSH01 | Rahul Gupta | UEGT10086 | Sitapur | MW | Ratish Dev Shukla | 9956167332
59 | 48529¦LAH01 | 02.07.2018 | 48529 |  | LAH01 | Rahul Gupta | UEGT10608 | Sitapur | MW | Surya Prakash Singh | 9956901615
60 | 48529¦DMR01 | 02.07.2018 | 48529 |  | DMR01 | Shambhu Nath | UEGT10615 | Basti | MW | Surendra Kumar Tripathi | 9792992998
62 | 48529¦BXS01 | 02.07.2018 | 48529 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | MW | Ram Lakhan | 9621911073
63 | 48529¦KZU01 | 02.07.2018 | 48529 |  | KZU01 | Rahul Gupta | UEGT11741 | Sitapur | 2MW | Ram Lakhan | 9621911073
64 | 48529¦KDZ01 | 02.07.2018 | 48529 |  | KDZ01 | Rahul Gupta | UEGT13356 | Shahjahanpur | 3MW | Praveen Kumar Yadav | 9721611872 | VIKASH SHUKLA
65 | 48529¦STP05 | 02.07.2018 | 48529 |  | STP05 | Rahul Gupta | UEGT10891 | Sitapur | 2MW | Ram Lakhan | 9621911073
66 | 48529¦BET01 | 02.07.2018 | 48529 |  | BET01 | Shambhu Nath | UEGT12437 | Gorakhpur | 2MW | Satya Prakash Singh | 7317503030
67 | 48529¦BGZ01 | 02.07.2018 | 48529 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735
68 | 48572¦BPO01 | 03.07.2018 | 48572 |  | BPO01 | Rahul Gupta | UEGT12206 | Lakhimpur | MW | Shakeel Mirza | 8009937140
69 | 48572¦LKSH08 | 03.07.2018 | 48572 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | MW | Manik Chandra | 7080861480
71 | 48572¦ADH01 | 03.07.2018 | 48572 |  | ADH01 | Rahul Gupta | UEGT11652 | Lko Nsc | MW | Shiv Shankar | 9936028884 | VIKASH SHUKLA
72 | 48572¦JTH01 | 03.07.2018 | 48572 |  | JTH01 | Rahul Gupta | UEGT12390 | Lakhimpur | MW | Sunil Kumar Gupta | 9984999462
73 | 48572¦REU01 | 03.07.2018 | 48572 |  | REU01 | Rahul Gupta | UEGT10985 | Sitapur | MW | Amit Singh | 9936966940
74 | 48649¦CBD01 | 06.07.2018 | 48649 |  | CBD01 | Rahul Gupta | UEGT13393 | Shahjahanpur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Praveen Kumar Yadav | 9721611872
75 | 48649¦LKSH08 | 06.07.2018 | 48649 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | EW, EPM, GROUTING OF PANDULAM, LADDER | Manik Chandra | 7080861480
76 | 48649¦LKSH04 | 06.07.2018 | 48649 |  | LKSH04 | Rahul Gupta | UEGT10125 | Sitapur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Pawan Kumar Mishra | 9956493163
77 | 48649¦DMZ01 | 06.07.2018 | 48649 |  | DMZ01 | Rahul Gupta | UEGT13021 | Sitapur | EW, EPM, GROUTING OF PANDULAM, LADDER | Awatar Singh | 9984496285
78 | 48649¦KNSH09 | 06.07.2018 | 48649 |  | KNSH09 | Rahul Gupta | UEGT10447 | Shahjahanpur | EW, 4EPM, GROUTING OF PANDULAM, LADDER | OM Prakash Singh | 9919901002
79 | 48649¦BRM01 | 06.07.2018 | 48649 |  | BRM01 | Rahul Gupta | UEGT12356 | Sitapur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Pawan Kumar Mishra | 9956493163
80 | 48649¦AUB01 | 06.07.2018 | 48649 |  | AUB01 | Rahul Gupta | UEGT11095 | Sitapur | EW, GROUTING OF PANDULAM, LADDER | Amit Kumar Mishra | 9648474341
81 | 48649¦AJP01 | 06.07.2018 | 48649 |  | AJP01 | Rahul Gupta | UEGT11100 | Sitapur | T/RACK & EW | Amit Singh | 9936966940
82 | 48649¦MOO01 | 06.07.2018 | 48649 |  | MOO01 | Rahul Gupta | UEGT13209 | Sitapur | T/RACK & EW | Amit Singh | 9936966940
83 | 48649¦LUK222 | 06.07.2018 | 48649 |  | LUK222 | Rahul Gupta | UERT11681 | Lko Scs | MW IP 55 & EW | Sarvesh Kumar | 9936309777
84 | 48649¦LUK147 | 06.07.2018 | 48649 |  | LUK147 | Rahul Gupta | UERT11490 | Lko Scn | EW, MH, LADDER & PANDULAM | Sachin Tomar | 9758655572
85 | 48649¦MJA01 | 06.07.2018 | 48649 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EW, BB & EPM | Harvansh Mani Tripathi | 9565065366

## WORK COMPLETION SHEET
SL. NO. | HELPER | PO DATE | PO NO. | SO. NO. | SITE ID | ZDM | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | VENDOR' NAME | STATUS | SITE ALLOTTED BY | COMPLETION DATE | JMR STATUS
0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | PREPARED/NOT PREPARED | SIBMISSION DATE | RECEIVED DATE
1 | 46883¦FTP01 | 19.04.2018 | 46883 |  | FTP01 | Rahul Gupta | UEGT10596 | Lko Nsc | BB, MH, EW & Chiller | 9935096993 | Amit Kumar Pandey | SATYA PRAKASH | COMPLETED |  | 29.04.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0585
2 | 46883¦MCH01 | 19.04.2018 | 46883 |  | MCH01 | Rahul Gupta | UEGT10980 | Sitapur | BB, MH, EW & Chiller | 9935096993 | Amit Kumar Mishra | TIWARI/SATYA PRAKASH | COMPLETED |  | 29.04.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0582
3 | 46851¦LKKN02 | 13.04.2018 | 46851 |  | LKKN02 | Rahul Gupta | UEGT10128 | Lko Nsc | 3EPM | 9935096993 | Ambika Parsad Yadav | RAMESH | COMPLETED |  | 12.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0581
4 | 46902¦STP02 | 18.04.2018 | 46902 |  | STP02 | Rahul Gupta | UERT10248 | Sitapur | MW | 9935096993 | Ram Lakhan | VIKAS SHULKA | COMPLETED |  | 01.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
5 | 46902¦SBD01 | 18.04.2018 | 46902 |  | SBD01 | Rahul Gupta | UEGT10408 | Shahjahanpur | MW | 9935096993 | Ajay Verma | VIKAS SHULKA | COMPLETED |  | 01.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
6 | 46902¦LUK95 | 18.04.2018 | 46902 |  | LUK95 | Rahul Gupta | UERT10833 | Lko Scn | MW | 9935096993 | Dinesh Kumar Dubey | VIKAS SHULKA | COMPLETED |  | 02.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
7 | 46902¦LUK166 | 18.04.2018 | 46902 |  | LUK166 | Rahul Gupta | UERT11974 | Lko Scn | MW | 9935096993 | Tarun Kumar Tiwari | VIKAS SHULKA | COMPLETED |  | 02.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
8 | 46845¦KUB01 | 13.04.2018 | 46845 |  | KUB01 | Shambhu Nath | UEGT10996 | Gorakhpur | EW | 9559961777 | Satya Kumar Shukla | SATYA PRAKASH | COMPLETED |  | 02.05.2018 | PREPARED | 02.05.2018 | 05.05.2018 | LTS/1819/0564
9 | 46902¦LUK124 | 18.04.2018 | 46902 |  | LUK124 | Rahul Gupta | UERT10863 | Lko Scs | 2MW | 9935096993 | Ranjeet Kumar Singh | VIKAS SHULKA | COMPLETED |  | 03.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
10 | 46902¦LUK73 | 18.04.2018 | 46902 |  | LUK73 | Rahul Gupta | UERT10307 | Lko Scn | MW | 9935096993 | Dinesh Kumar Dubey | VIKAS SHULKA | COMPLETED |  | 03.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
11 | 46902¦LUK98 | 18.04.2018 | 46902 |  | LUK98 | Rahul Gupta | UEGT17019 | Lko Scn | MW | 9935096993 | Tarun Kumar Tiwari | VIKAS SHULKA | COMPLETED |  | 03.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
12 | 46902¦LUK39 | 18.04.2018 | 46902 |  | LUK39 | Rahul Gupta | UEGT10001 | Lko Scn | MW | 9935096993 | Dinesh Kumar Dubey | VIKAS SHULKA | COMPLETED |  | 03.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
13 | 46902¦LUK87 | 18.04.2018 | 46902 |  | LUK87 | Rahul Gupta | UERT11093 | Lko Scn | MW | 9935096993 | Ashutosh Kumar | VIKAS SHULKA | COMPLETED |  | 04.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
14 | 46902¦LUK59 | 18.04.2018 | 46902 |  | LUK59 | Rahul Gupta | UERT10309 | Lko Scs | 3MW | 9935096993 | Sarvesh Kumar | VIKAS SHULKA | COMPLETED |  | 04.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
15 | 46902¦LUK36 | 18.04.2018 | 46902 |  | LUK36 | Rahul Gupta | UERT10041 | Lko Scn | 3MW | 9935096993 | Anuj Kumar Tiwari | VIKAS SHULKA | COMPLETED |  | 04.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0580
16 | 47162¦SDN01 | 02.05.2018 | 47162 |  | SDN01 | Shambhu Nath | UEGT10512 | Basti | AC FOUNDATION (O&M) | 9559961777 | PradeeP Kumar Mishra | Surrender TIWARI | COMPLETED |  | 04.05.2018 | PREPARED | 16.05.2018 |  | #N/A
17 | 46924¦GKP50 | 19.04.2018 | 46924 |  | GKP50 | Shambhu Nath | UERT11134 | Gorakhpur | MW | 9559961777 | Dharmendra Pandey | VIKAS SHULKA | COMPLETED |  | 10.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0626
18 | 46924¦GKP51 | 19.04.2018 | 46924 |  | GKP51 | Shambhu Nath | UERT11146 | Gorakhpur | MW | 9559961777 | Dharmendra Pandey | VIKAS SHULKA | COMPLETED |  | 10.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0626
19 | 47092¦TUW01 | 27.04.2018 | 47092 |  | TUW01 | Shambhu Nath | UEGT13163 | Maharajganj | 3EPM & 1IP55 | 9559961777 | Ajay Kumar Singh | VIKAS SHULKA | COMPLETED |  | 11.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0616
20 | 46924¦ABZ01 | 19.04.2018 | 46924 |  | ABZ01 | Shambhu Nath | UEGT12658 | Maharajganj | 3EPM | 9559961777 | Ajay Kumar Singh | VIKAS SHULKA | COMPLETED |  | 11.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0626
21 | 46974¦FZL01 | 23.04.2018 | 46974 |  | FZL01 | Shambhu Nath | UEGT11749 | Maharajganj | EW,MWIP55 & MRBTS MOUNT,3EPM | 9559961777 | Vipin Kumar Yadav | VIKAS SHULKA | COMPLETED |  | 12.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0614
22 | 47027¦DRG01 | 25.04.2018 | 47027 |  | DRG01 | Shambhu Nath | UEGT10739 | Mau | MW | 9559961777 | Sanjay Kumar Singh | VIKAS SHULKA | COMPLETED |  | 12.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0627
23 | 47031¦SHPL01 | 25.04.2018 | 47031 |  | SHPL01 | Rahul Gupta | UEGT10829 | Shahjahanpur | Pest Control | 9935096993 | Bhoopendra Singh | TECHNICIAN | COMPLETED |  | 14.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0584
24 | 47029¦JRL01 | 25.04.2018 | 47029 |  | JRL01 | Rahul Gupta | UEGT10932 | Sitapur | EW & BB | 9935096993 | Surya Prakash Singh | SONU SINGH | COMPLETED |  | 15.05.2017 | PREPARED | 18.05.2018 | 18.05.2018 | LTS/1819/0599
25 | 46902¦KSL01 | 18.04.2018 | 46902 |  | KSL01 | Rahul Gupta | UEGT13118 | Sitapur | EW & TRANSMISSION RACK | 9935096993 | Ram Lakhan | SONU SINGH | COMPLETED |  | 15.05.2017 | PREPARED | 18.05.2018 | 18.05.2018 | LTS/1819/0601
26 | 47023¦LKRB02 | 25.4.2018 | 47023 |  | LKRB02 | Rahul Gupta | UEGT10233 | Lko Nsc | EW & TRANSMISSION RACK | 9935096993 | Ashish Kumar Singh | SONU SINGH | COMPLETED |  | 16.05.2017 | PREPARED | 18.05.2018 | 18.05.2018 | LTS/1819/0600
27 | 47324¦BUG01 | 08.05.2018 | 47324 |  | BUG01 | Dharmbir | UEGT12302 | Balia | PENDULAM3,EW,2EPM,LADDER3,DISM. OF PIU,DISM. OF SMPS,MH | 9559196969 | Jugal Kishore Mishra | ANOOP | COMPLETED |  | 11.05.2018 | PREPARED |  |  | LTS/1819/0621
28 | 47002¦BST02 | 24.04.2018 | 47002 |  | BST02 | Shambhu Nath | UEGT10244 | Basti | EW,Transmission rack | 9559961777 | BiPin Kumar Singh | NOOR AHMAD | COMPLETED |  | 13.05.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0594
29 | 47003¦JAL01 | 24.04.2018 | 47003 |  | JAL01 | Rahul Gupta | UEGT10423 | Shahjahanpur | Pest Control | 9935096993 | Praveen Kumar Yadav | TECHNICIAN | COMPLETED |  | 15.05.2017 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0583
30 | 47023¦LKVN03 | 25.4.2018 | 47023 |  | LKVN03 | Rahul Gupta | UEGT10138 | Lko Nsc | EW & TRANSMISSION RACK | 9935096993 | Ran Vijay Singh | SONU SINGH | COMPLETED |  | 18.05.2018 | PREPARED | 18.05.2018 | 18.05.2018 | LTS/1819/0600
31 | 46950¦PHR01 | 20.04.2018 | 46950 |  | PHR01 | Sumit Mohan | UEGT10350 | Pratapgarh | O&M EB Maintenance | 9935949991 | KAMAL KUMAR SINGH | DEVENDRA PANDEY | COMPLETED |  | 16.05.2018 | PREPARED | 17.05.2018 |  | #N/A
32 | 47002¦KDR01 | 24.04.2018 | 47002 |  | KDR01 | Shambhu Nath | UEGT13170 | Gorakhpur | EW & TRANSMISSION RACK | 9559961777 | Santosh Jaiswal | SATYA PRAKASH | COMPLETED |  | 16.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0628
33 | 47002¦COT01 | 24.04.2018 | 47002 |  | COT01 | Shambhu Nath | UEGT11891 | Mau | EW & TRANSMISSION RACK | 9559961777 | Akhilesh Singh | NOOR AHMAD | COMPLETED |  | 16.05.2018 |  |  |  | #N/A
34 | 47597¦NAA01 | 21.05.2018 | 47597 | SO699961 | NAA01 | Shambhu Nath | UEGT13529 | Basti | 3 EPM,MW IP55 & EW | 9559961777 | Rajesh Kumar Yadav | VIKAS SHULKA | COMPLETED BUT EW PENDING |  | 13.06.2018 | PREPARED |  |  | #N/A
35 | 47029¦IPC01 | 25.04.2018 | 47029 |  | IPC01 | Rahul Gupta | UERT12141 | Lko Nsc | MW | 9935096993 | Amit Kumar Pandey | VIKAS SHULKA | COMPLETED |  | 26.05.2018 | SITE HOLD |  |  | #N/A
36 | 46902¦LUK29 | 18.04.2018 | 46902 |  | LUK29 | Rahul Gupta | UERT10074 | Lko Scn | 2MW | 9935096993 | Dinesh Kumar Dubey | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0598
37 | 46902¦LKGP01 | 18.04.2018 | 46902 |  | LKGP01 | Rahul Gupta | UEGT10288 | Lko Nsc | MW | 9935096993 | Imran Khan | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0597
38 | 46902¦LUK34 | 18.04.2018 | 46902 |  | LUK34 | Rahul Gupta | UERT10063 | Lko Scn | MW | 9935096993 | Sachin Tomar | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0598
39 | 46902¦LUK104 | 18.04.2018 | 46902 |  | LUK104 | Rahul Gupta | UEGT10808 | Lko Scs | MW | 9935096993 | Krishna Murari Singh | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0580
40 | 46902¦LUK27 | 18.04.2018 | 46902 |  | LUK27 | Rahul Gupta | UERT10008 | Lko Scs | MW | 9935096993 | Mangla Prasad | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0598
41 | 46902¦LUK148 | 18.04.2018 | 46902 |  | LUK148 | Rahul Gupta | UEGT10902 | Lko Scs | MW | 9935096993 | Krishna Murari Singh | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0580
42 | 46902¦LUK31 | 18.04.2018 | 46902 |  | LUK31 | Rahul Gupta | UERT10061 | Lko Scn | 3MW | 9935096993 | Ashutosh Kumar | RAMESH | COMPLETED |  | 19.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0598
43 | 47488¦LSK01 | 19.05.2018 | 47488 |  | LSK01 | Rahul Gupta | UEGT12029 | Lko Nsc | MW | 9935096993 | Ashish Kumar Singh | VIKAS SHULKA | COMPLETED |  | 26.05.2018 | PREPARED |  |  | LTS/1819/0645
44 | 47469¦KRS01 | 15.05.2018 | 47469 |  | KRS01 | Rahul Gupta | UEGT10836 | Sitapur | MW IP55 | 9935096993 | Dileep Kumar | VIKAS SHULKA | COMPLETED |  | 21.05.2018 | PREPARED | 01.06.2018 |  | LTS/1819/0642
45 | 47469¦DFP01 | 15.05.2018 | 47469 |  | DFP01 | Rahul Gupta | UEGT11875 | Sitapur | MW IP55 | 9935096993 | Dileep Kumar | VIKAS SHULKA | COMPLETED |  | 21.05.2018 | PREPARED | 01.06.2018 |  | LTS/1819/0642
46 | 47469¦PMP01 | 15.05.2018 | 47469 |  | PMP01 | Jitender Chaturvedi | UEGT13419 | Gonda | 3 EPM & MW IP55 | 7317850960 | Ram Swaraj Verma | VIKAS SHULKA | COMPLETED |  | 21.05.2018 | PREPARED | 01.06.2018 |  | LTS/1819/0647
47 | 47469¦LUK182 | 15.05.2018 | 47469 |  | LUK182 | Rahul Gupta | UERT11493 | Lko Scs | MW | 9935096993 | Ganga Sagar |  | COMPLETED |  |  | PREPARED | 01.06.2018 |  | #N/A
48 | 47469¦LKGP18 | 15.05.2018 | 47469 |  | LKGP18 | Rahul Gupta | UEGT10521 | Lko Nsc | MW IP55 | 9935096993 | Imran Khan | VIKAS SHULKA | COMPLETED |  | 21.05.2018 | PREPARED | 01.06.2018 |  | LTS/1819/0642
49 | 47469¦LUK90 | 15.05.2018 | 47469 |  | LUK90 | Rahul Gupta | UERT10880 | Lko Scs | MW | 9935096993 | Mangla Prasad |  | COMPLETED |  |  | PREPARED | 01.06.2018 |  | #N/A
50 | 47027¦CUC01 | 25.04.2018 | 47027 |  | CUC01 | Shambhu Nath | UEGT13136 | Deoria | MW | 9559961777 | Sanjog Ku.Singh | Deepak singh | COMPLETED |  | 25.05.2018 | PREPARED |  |  | #N/A
51 | 47469¦NGP01 | 15.05.2018 | 47469 |  | NGP01 | Shambhu Nath | UEGT11257 | Deoria | MW IP55 | 9559961777 | Sanjog Ku.Singh | Deepak singh | COMPLETED |  | 25.05.2018 | PREPARED |  |  | LTS/1819/0656
52 | 47469¦SIF01 | 15.05.2018 | 47469 |  | SIF01 | Jitender Chaturvedi | UEGT12108 | Sultanpur | 3 EPM,MW IP55 & EW | 7317850960 | RAM KISHORE YADAV | SR687571 | COMPLETED |  | 25.05.2018 | PREPARED |  |  | LTS/1819/0647
53 | 47602¦BGZ01 | 21.05.2018 | 47602 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | EW | 9935096993 | Sujeet Kumar Singh |  | COMPLETED |  | 25.05.2018 | PREPARED | 01.06.2018 |  | LTS/1819/0639
54 | 46902¦LUK17 | 18.04.2018 | 46902 |  | LUK17 | Rahul Gupta | UERT10254 | Lko Scs | MW | 9935096993 | Ganga Sagar | VIKAS SHULKA | COMPLETED |  | 25.05.2018 | PREPARED | 16.05.2018 | 16.05.2018 | LTS/1819/0580
55 | 47469¦KPB01 | 15.05.2018 | 47469 |  | KPB01 | Shambhu Nath | UEGT12560 | Deoria | 3 EPM & MW IP55 | 9559961777 | Sher Bahadur Singh | Deepak singh | EPM COMPLETED MW NOT AVAILABLE |  | 25.05.2018 | PREPARED |  |  | LTS/1819/0656
56 | 46851¦LKSH09 | 13.04.2018 | 46851 |  | LKSH09 | Rahul Gupta | UEGT10261 | Shahjahanpur | 3EPM | 9935096993 | Praveen Kumar Yadav | VIKAS SHULKA | COMPLETED |  | 01.05.2018 | PREPARED | 15.05.2018 | 15.05.2018 | LTS/1819/0581
57 | 47530¦LKSH05 | 17.05.2018 | 47530 |  | LKSH05 | Rahul Gupta | UEGT10258 | Sitapur | EPM | 9935096993 | Ram Lakhan | VIKAS SHULKA | COMPLETED |  | 26.05.2018 | PREPARED |  |  | #N/A
58 | 47530¦BLN01 | 17.05.2018 | 47530 |  | BLN01 | Rahul Gupta | UEGT11966 | Lakhimpur | EPM | 9935096993 | Santosh Kumar Singh | VIKAS SHULKA | COMPLETED |  | 27.05.2018 | PREPARED |  |  | LTS/1819/0641
59 | 47742¦SDN02 | 28.05.2018 | 47742 |  | SDN02 | Shambhu Nath | UEGT11589 | Basti | 3 EPM,MW IP55 & EW | 9559961777 | PradeeP Kumar Mishra | 28-30,190,300 | COMPLETED BUT EW PENDING |  | 13.06.2018 | PREPARED |  |  | #N/A
60 | 47530¦PGL01 | 17.05.2018 | 47530 |  | PGL01 | Rahul Gupta | UEGT12116 | Lakhimpur | EPM | 9935096993 | Santosh Kumar Singh | VIKAS SHULKA | COMPLETED |  | 27.05.2018 | PREPARED |  |  | LTS/1819/0641
61 | 47469¦BGZ01 | 15.05.2018 | 47469 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | 3 EPM & MW IP55 | 9935096993 | Sujeet Kumar Singh |  | COMPLETED |  |  | PREPARED | 01.06.2018 |  | LTS/1819/0642
62 | 47530¦SJK01 | 17.05.2018 | 47530 |  | SJK01 | Rahul Gupta | UEGT13076 | Lakhimpur | EPM | 9935096993 | Sunil Kumar Gupta | VIKAS SHULKA | COMPLETED |  | 27.05.2018 | PREPARED |  |  | LTS/1819/0641
63 | 47602¦GCH01 | 21.05.2018 | 47602 |  | GCH01 | Rahul Gupta | UEGT11876 | Sitapur | EPM | 9935096993 | Vivek Singh | VIKAS SHULKA | COMPLETED |  | 27.05.2018 | PREPARED |  |  | LTS/1819/0639
64 | 47597¦MPO01 | 21.05.2018 | 47597 |  | MPO01 | Shambhu Nath | UEGT12336 | Deoria | 3 EPM,MW IP55 & EW | 9559961777 | Prasidha Kumar Mishra | Deepak singh | COMPLETED BUT EW PENDING |  | 28.05.2018 | PREPARED |  |  | LTS/1819/0657
65 | 47469¦SSY01 | 15.05.2018 | 47469 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | 3 EPM & MW IP55 | 9559961777 | Sher Bahadur Singh | Deepak singh | EPM COMPLETED MW NOT AVAILABLE |  | 30.05.2018 | PREPARED |  |  | LTS/1819/0656
66 | 47530¦GZR01 | 17.05.2018 | 47530 |  | GZR01 | Shambhu Nath | UEGT11514 | Kushi Nagar | EPM | 9559961777 | Ramesh ku. Gaur | Deepak singh | COMPLETED |  | 31.05.2018 | PREPARED |  |  | LTS/1819/0658
67 | 46793¦LUK113 | 10.04.2018 | 46793 |  | LUK113 | Rahul Gupta | UERT10943 | Lko Scn | CIVIL | 9935096993 | Anuj Kumar Tiwari | Surrender TIWARI |  |  |  | PREPARED | 30.06.2018 | 30.06.2018 | LTS/1819/0634
68 | 47469¦PGH01 | 15.05.2018 | 47469 |  | PGH01 | Shambhu Nath | UEGT11709 | Kushi Nagar | 3 EPM & MW IP55 | 9559961777 | Ramesh ku. Gaur | Deepak singh | EPM COMPLETED MW NOT AVAILABLE |  | 01.05.2018 | PREPARED |  |  | LTS/1819/0656
69 | 47597¦GDE01 | 21.05.2018 | 47597 |  | GDE01 | Rahul Gupta | UEGT11089 | Sitapur | EW | 9935096993 | Vivek Singh | SATYA PRAKASH | COMPLETED |  | 01.05.2018 | PREPARED |  |  | LTS/1819/0644
70 | 47469¦SNPD07 | 15.05.2018 | 47469 |  | SNPD07 | Shambhu Nath | UEGT10424 | Kushi Nagar | MW | 9559961777 | Vijay Kumar Patel | Deepak singh | COMPLETED |  | 01.05.2018 | PREPARED |  |  | LTS/1819/0656
71 | 47670¦SWQ01 | 23.05.2018 | 47670 |  | SWQ01 | Dharmbir | UEGT13415 | Sonbhdra | MW | 9559196969 | Ajay Kumar Singh | VIKAS SHULKA | COMPLETED |  | 02.06.2018 | PREPARED |  |  | LTS/1819/0654
72 | 47530¦PRK01 | 17.05.2018 | 47530 |  | PRK01 | Shambhu Nath | UEGT11834 | Kushi Nagar | EPM | 9559961777 | Animesh Kumar | Deepak singh | COMPLETED |  | 02.06.2018 | PREPARED |  |  | LTS/1819/0658
73 | 46265¦PTE01 | 13.03.2018 | 46265 |  | PTE01 | Shambhu Nath | UEGT12048 | Kushi Nagar | DCDB | 9559961777 | Bhasker Awasti | Deepak singh | COMPLETED |  | 02.06.2018 | PREPARED |  |  | LTS/1819/0587
74 | 47469¦NTW01 | 15.05.2018 | 47469 |  | NTW01 | Shambhu Nath | UEGT12034 | Maharajganj | 3 EPM & MW IP55 | 9559961777 | Harendra Kumar Patel | Deepak singh | EPM COMPLETED MW NOT AVAILABLE |  | 03.06.2018 | PREPARED |  |  | LTS/1819/0656
75 | 46924¦ABZ01 | 19.04.2018 | 46924 |  | ABZ01 | Shambhu Nath | UEGT12658 | Maharajganj | EW(29000) DG GREED | 9559961777 | Ajay Kumar Singh | NOOR AHMAD | COMPLETED |  | 03.06.2018 | PREPARED | 16.05.2018 |  | LTS/1819/0626
76 | 47743¦KRD01 | 28.05.2018 | 47743 |  | KRD01 | Rahul Gupta | UEGT12793 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | 9935096993 | Ashutosh Kumar | ANOOP | COMPLETED |  | 04.06.2018 | PREPARED |  |  | #N/A
77 | 47469¦SRH01 | 15.05.2018 | 47469 |  | SRH01 | Shambhu Nath | UEGT11338 | Maharajganj | 3 EPM & MW IP55 | 9559961777 | Harendra Kumar Patel | Deepak singh | COMPLETED |  | 04.06.2018 | PREPARED |  |  | LTS/1819/0656
78 | 47469¦MJC01 | 15.05.2018 | 47469 |  | MJC01 | Shambhu Nath | UEGT12215 | Maharajganj | 2EPM | 9559961777 | Vipin Kumar Yadav | Deepak singh | COMPLETED |  | 04.06.2018 | PREPARED |  |  | LTS/1819/0656
79 | 47938¦ATA01 | 04.06.2018 | 47938 |  | ATA01 | Rahul Gupta | UEGT11344 | Lko Nsc | MW | 9935096993 | Sujeet Kumar Singh | VIKAS SHULKA | COMPLETED |  | 12.06.2018 | NOT PREPARED |  |  | #N/A
80 | 47386¦TUW01 | 09.05.2018 | 47386 |  | TUW01 | Shambhu Nath | UEGT13163 | Maharajganj | EW(29000) DG GREED | 9559961777 | Ajay Kumar Singh | NOOR AHMAD | COMPLETED |  | 04.06.2018 | PREPARED |  |  | LTS/1819/0666
81 | 47530¦SNB01 | 17.05.2018 | 47530 |  | SNB01 | Shambhu Nath | UEGT11058 | Maharajganj | EPM | 9559961777 | Parshuram Gupta | Deepak singh | COMPLETED |  | 05.06.2018 | PREPARED |  |  | LTS/1819/0658
82 | 47597¦MUT01 | 21.05.2018 | 47597 |  | MUT01 | Shambhu Nath | UEGT12763 | Maharajganj | 3 EPM,MW IP55 & EW | 9559961777 | Girijesh Gupta | Deepak singh | 3EPM DONE, MW NOT AVAILABLE & INSTALLATION OF T/RACK DONE |  | 06.06.2018 | NOT PREPARED FOR T/RACK installation only |  |  | LTS/1819/0657
83 | 47597¦CHM01 | 21.05.2018 | 47597 |  | CHM01 | Shambhu Nath | UEGT11246 | Maharajganj | CIVIL (1.2X1.2),EW,LADDER & PENDULUM | 9559961777 | Parshuram Gupta | NOOR AHMAD | COMPLETED WID T/RACK |  | 06.06.2018 | NOT PREPARED FOR T/RACK |  |  | #N/A
84 | 47602¦LIL01 | 21.05.2018 | 47602 |  | LIL01 | Dharmbir | UEGT12587 | Balia | EPM | 9559196969 | Rajesh. Pandey | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0655
85 | 47602¦SNW01 | 21.05.2018 | 47602 |  | SNW01 | Dharmbir | UEGT12633 | Balia | EPM | 9559196969 | Amit Kumar Pandey | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0655
86 | 47670¦GKVN17 | 23.05.2018 | 47670 |  | GKVN17 | Dharmbir | UEGT10667 | Balia | MW | 9559196969 | Jugal Kishore Mishra | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
87 | 47670¦KMT01 | 23.05.2018 | 47670 |  | KMT01 | Dharmbir | UEGT13238 | Balia | MW | 9559196969 | Pawan Kumar Rai | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
88 | 47602¦BAN02 | 21.05.2018 | 47602 |  | BAN02 | Dharmbir | UEGT12595 | Balia | EPM | 9559196969 | Naveen Kumar Rai | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0655
89 | 47602¦KJH01 | 21.05.2018 | 47602 |  | KJH01 | Dharmbir | UEGT11936 | Balia | EPM | 9559196969 | Rajesh. Pandey | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0655
90 | 47670¦KIU01 | 23.05.2018 | 47670 |  | KIU01 | Dharmbir | UEGT12349 | Varanasi | MW | 9559196969 | Pramod Kumar Singh | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
91 | 47670¦VNS22 | 23.05.2018 | 47670 |  | VNS22 | Dharmbir | UEGT10117 | Varanasi | MW | 9559196969 | Rakesh Kumar. | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
92 | 47670¦BDG01 | 23.05.2018 | 47670 |  | BDG01 | Dharmbir | UEGT10753 | Varanasi | MW | 9559196969 | Pramod Kumar Singh | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
93 | 47670¦VNS02 | 23.05.2018 | 47670 |  | VNS02 | Dharmbir | UERT10083 | Varanasi | MW | 9559196969 | Rakesh Kumar | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
94 | 47670¦ABI01 | 23.05.2018 | 47670 |  | ABI01 | Dharmbir | UEGT12216 | Mirzapur | MW | 9559196969 | Inderjeet Pathak | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
95 | 47670¦VNS30 | 23.05.2018 | 47670 |  | VNS30 | Dharmbir | UERT10278 | Varanasi | MW | 9559196969 | Manish Kumar Sharma. | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
96 | 47670¦MGRN01 | 23.05.2018 | 47670 |  | MGRN01 | Dharmbir | UEGT10485 | Sonbhdra | MW | 9559196969 | Piyush Sharma | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
97 | 47670¦VNS27 | 23.05.2018 | 47670 |  | VNS27 | Dharmbir | UEGT10174 | Varanasi | MW | 9559196969 | Sunil Kumar Tiwari | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
98 | 47670¦KNK01 | 23.05.2018 | 47670 |  | KNK01 | Dharmbir | UEGT12394 | Sonbhdra | MW | 9559196969 | Ajay Kumar Singh | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
99 | 47670¦BUS01 | 23.05.2018 | 47670 |  | BUS01 | Dharmbir | UEGT12765 | Balia | MW | 9559196969 | Arvind Yadav | VIKAS SHULKA | COMPLETED |  | 06.06.2018 | PREPARED |  |  | LTS/1819/0654
100 | 47671¦GKP41 | 23.05.2018 | 47671 |  | GKP41 | Shambhu Nath | UERT10770 | Gorakhpur | EW (37000) | 9559961777 | Dharmendra Pandey | NOOR AHMAD | DCDB COMPLETED |  | 07.06.2018 | PREPARED |  |  | #N/A
101 | 47670¦SLO01 | 23.05.2018 | 47670 |  | SLO01 | Dharmbir | UEGT12268 | Mirzapur | 3 MW | 9559196969 | Inderjeet Pathak | VIKAS SHULKA | Completed |  | 07.06.2018 | PREPARED |  |  | LTS/1819/0654
102 | 47469¦BCG01 | 15.05.2018 | 47469 | SO678615 | BCG01 | Shambhu Nath | UEGT13383 | Maharajganj | 3 EPM,MW IP55 & EW | 9559961777 | Santosh Kumar Yadav | Deepak singh | MW not available |  | 07.06.2018/27.06.2018 | PREPARED |  |  | LTS/1819/0656
103 | 47002¦ABZ01 | 24.04.2018 | 47002 |  | ABZ01 | Shambhu Nath | UEGT12658 | Maharajganj | MWIP55 | 9559961777 | Ajay Kumar Singh | Deepak singh | COMPLETED |  | 08.06.2018 | PREPARED |  |  | LTS/1819/0664
104 | 47602¦UNK01 | 21.05.2018 | 47602 |  | UNK01 | Rahul Gupta | UEGT12818 | Shahjahanpur | CIVIL (1.2X1.2),EW & MH | 9935096993 | Bhoopendra Singh | ANOOP/SATYA PRAKASH | COMPLETED |  | 08.06.2018 | PREPARED |  |  | LTS/1819/0639
105 | 47602¦SZA01 | 21.05.2018 | 47602 |  | SZA01 | Rahul Gupta | UEGT13045 | Shahjahanpur | EW | 9935096993 | Bhoopendra Singh | SATYA PRAKASH | COMPLETED |  | 08.06.2018 | PREPARED |  |  | LTS/1819/0652
106 | 47031¦ANL01 | 25.04.2018 | 47031 |  | ANL01 | Rahul Gupta | UEGT13033 | Shahjahanpur | Pest Control | 9935096993 | Raghuveer Singh Yadav | LAKHAN | COMPLETED |  | 05.06.2018 | PREPARED |  |  | LTS/1819/0649
107 | 47031¦LKSH09 | 25.04.2018 | 47031 |  | LKSH09 | Rahul Gupta | UEGT10261 | Shahjahanpur | Pest Control | 9935096993 | Praveen Kumar Yadav | LAKHAN | COMPLETED |  | 05.06.2018 | PREPARED |  |  | LTS/1819/0649
108 | 47031¦AST01 | 25.04.2018 | 47031 |  | AST01 | Rahul Gupta | UEGT11901 | Sitapur | Pest Control | 9935096993 | Ratish Dev Shukla | LAKHAN | COMPLETED |  | 05.06.2018 | PREPARED |  |  | LTS/1819/0649
109 | 47602¦SUZ01 | 21.05.2018 | 47602 |  | SUZ01 | Rahul Gupta | UEGT12888 | Shahjahanpur | EW | 9935096993 | OM Prakash Singh | SATYA PRAKASH | COMPLETED |  | 08.06.2018 | PREPARED |  |  | LTS/1819/0652
110 | 47597¦BCR01 | 21.05.2018 | 47597 |  | BCR01 | Shambhu Nath | UEGT13477 | Maharajganj | 3 EPM,MW IP55 & EW | 9559961777 | Ajay Kumar Yadav | Deepak singh & NOOR | COMPLETED ONLY IP 55 NOT AVAILABLE |  | 09.06.2018 | PREPARED |  |  | #N/A
111 | 47469¦GKPP01 | 15.05.2018 | 47469 | SO667013 | GKPP01 | Shambhu Nath | UEGT10630 | Maharajganj | 3 EPM & MW IP55 | 9559961777 | SachidaNand Yadav | Deepak singh | COMPLETED ONLY IP 55 NOT AVAILABLE |  | 10.06.2018 | PREPARED |  |  | #N/A
112 | 47955¦SFL01 | 05.06.2018 | 47955 |  | SFL01 | Shambhu Nath | UEGT12792 | Basti | O&M EB Maintenance | 9559961777 | BiPin Kumar Singh | TECHNICIAN | COMPLETED |  | 11.06.2018 | PREPARED |  |  | LTS/1819/0667
113 | 47941¦RLA01 | 04.06.2018 | 47941 |  | RLA01 | Shambhu Nath | UEGT12503 | Kushi Nagar | MW | 9559961777 | RuPnath Paswan | Deepak singh | COMPLETED |  | 11.06.2018 | PREPARED |  |  | #N/A
114 | 47868¦HPH01 | 31.05.2018 | 47868 |  | HPH01 | Shambhu Nath | UEGT12150 | Kushi Nagar | MW | 9559961777 | RuPnath Paswan | Deepak singh | COMPLETED |  | 11.06.2018 | PREPARED | 32-13 |  | #N/A
115 | 47735¦MWG01 | 28.05.2018 | 47735 |  | MWG01 | Shambhu Nath | UEGT12015 | Kushi Nagar | DISM. OF SMPS & PIU | 9559961777 | Ravinder Kumar Singh | HARIKESH SPACE TELICOM | COMPLETED |  | 13.06.2018 | PREPARED |  |  | #N/A
116 | 47742¦TYB01 | 28.05.2018 | 47742 |  | TYB01 | Shambhu Nath | UEGT12952 | Basti | 3 EPM,MW IP55 & EW | 9559961777 | Arun Kumar TriPathi | VIKAS SHULKA | COMPLETED & EW pending |  | 14.06.2018 | PREPARED |  |  | #N/A
117 | 47023¦HPR01 | 25.4.2018 | 47023 |  | HPR01 | Rahul Gupta | UERT12746 | Lakhimpur | EW & TRANSMISSION RACK | 9935096993 | Santosh Kumar Singh | SATYA PRAKASH | COMPLETED |  | 15.06.2018 | PREPARED |  |  | LTS/1819/0643
118 | 47029¦LKVN18 | 25.04.2018 | 47029 |  | LKVN18 | Rahul Gupta | UEGT10507 | Lko Nsc | MW | 9935096993 | Ran Vijay Singh | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | LTS/1819/0640
119 | 47469¦JSK01 | 15.05.2018 | 47469 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | 3 EPM & MW IP55 | 9935096993 | Ran Vijay Singh | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | #N/A
120 | 47602¦RKK01 | 21.05.2018 | 47602 |  | RKK01 | Rahul Gupta | UEGT13298 | Lakhimpur | EPM | 9935096993 | Sunil Kumar Gupta | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | LTS/1819/0639
121 | 47530¦SKQ01 | 17.05.2018 | 47530 |  | SKQ01 | Rahul Gupta | UEGT13552 | Sitapur | EPM | 9935096993 | Surya Prakash Singh | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | LTS/1819/0641
122 | 47530¦HZD01 | 17.05.2018 | 47530 |  | HZD01 | Rahul Gupta | UEGT13024 | Lakhimpur | EPM | 9935096993 | Mohd. Shahid Khan | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | #N/A
123 | 47743¦KIM01 | 28.05.2018 | 47743 |  | KIM01 | Rahul Gupta | UEGT12153 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | 9935096993 | Ashutosh Kumar | ANOOP/VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | LTS/1819/0653
124 | 47878¦NPW01 | 01.06.2018 | 47878 |  | NPW01 | Rahul Gupta | UEGT12835 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | 9935096993 | Harvansh Mani Tripathi | ANOOP | COMPLETED |  | 15.06.2018 | PREPARED |  |  | LTS/1819/0651
125 | 47916¦STSH04 | 02.06.2018 | 47916 | SO704992 | STSH04 | Rahul Gupta | UEGT10605 | Lakhimpur | EW | 9935096993 | Ashutosh Kumar | VIKAS SHULKA | COMPLETED |  | 15.06.2018 |  |  |  | #N/A
126 | 47556¦MAU02 | 21.05.2018 | 47556 |  | MAU02 | Shambhu Nath | UEGT10534 | Mau | Pest Control | 9559961777 | Akhilesh Singh | KANHAIYA | COMPLETED |  | 15.06.2018 | NOT PREPARED |  |  | #N/A
127 | 47556¦GKP31 | 21.05.2018 | 47556 |  | GKP31 | Shambhu Nath | UEGT10911 | Gorakhpur | Pest Control | 9559961777 | Raghvendra Kumar Gautum | KANHAIYA | COMPLETED |  | 15.06.2018 | PREPARED |  |  | LTS/1819/0663
128 | 47735¦IDR01 | 28.05.2018 | 47735 |  | IDR01 | Shambhu Nath | UEGT12068 | Mau | DISM. OF SMPS & PIU | 9559961777 | Amit Kumar Srivastava | ANOOP | COMPLETED |  | 15.06.2018 | PREPARED |  |  | #N/A
129 | 47782¦IDR01 | 30.05.2018 | 47782 |  | IDR01 | Shambhu Nath | UEGT12068 | Mau | EW | 9559961777 | Amit Kumar Srivastava | ANOOP | COMPLETED |  | 15.06.2018 | PREPARED |  |  | #N/A
130 | 47530¦IDR01 | 17.05.2018 | 47530 | SO678331 | IDR01 | Shambhu Nath | UEGT12068 | Mau | EPM | 9559961777 | Amit Kumar Srivastava | ANOOP | COMPLETED |  | 15.06.2018 | PREPARED |  |  | #N/A
131 | 47868¦JSW01 | 31.05.2018 | 47868 |  | JSW01 | Shambhu Nath | UEGT11957 | Maharajganj | CIVIL(1.2X1.2) | 9559961777 | Vipin Kumar Yadav | ANOOP | PAD EXIST | [5 empty] | #N/A
132 | 47938¦CCG01 | 04.06.2018 | 47938 | SO706941 | CCG01 | Rahul Gupta | UEGT13036 | Lakhimpur | 2MW | 9935096993 | Harvansh Mani Tripathi | VIKAS SHULKA | COMPLETED |  | 18.06.2018 | PREPARED |  |  | #N/A
133 | 47597¦BNM01 | 21.05.2018 | 47597 | SO697239 | BNM01 | Shambhu Nath | UEGT12652 | Basti | 3 EPM,MW IP55 & EW | DINESH | 7521010900 | ANOOP | COMPLETED |  | 18.06.2018 | PREPARED |  |  | #N/A
134 | 47916¦NPW01 | 02.06.2018 | 47916 | SO705944 | NPW01 | Rahul Gupta | UEGT12835 | Lakhimpur | 3 EPM,MW IP55 & EW | 9935096993 | Harvansh Mani Tripathi | VIKAS SHULKA | COMPLETED & EW pending |  | 18.06.2018 | NOT PREPARED |  |  | #N/A
135 | 47938¦NPW01 | 04.06.2018 | 47938 | SO706931 | NPW01 | Rahul Gupta | UEGT12835 | Lakhimpur | 2MW | 9935096993 | Harvansh Mani Tripathi | VIKAS SHULKA | COMPLETED |  | 18.06.2018 | NOT PREPARED |  |  | #N/A
136 | 47938¦RGE01 | 04.06.2018 | 47938 | SO706900 | RGE01 | Rahul Gupta | UEGT12410 | Lakhimpur | MW | 9935096993 | Mukesh Kumar Mishra | VIKAS SHULKA | COMPLETED |  | 19.06.2018 | NOT PREPARED |  |  | #N/A
137 | 47962¦HPR01 | 05.06.2018 | 47962 | SO688277 | HPR01 | Rahul Gupta | UERT12746 | Lakhimpur | 2MW | 9935096993 | Santosh Kumar Singh | VIKAS SHULKA | COMPLETED |  | 19.06.2018 | NOT PREPARED |  |  | #N/A
138 | 47962¦LMP01 | 05.06.2018 | 47962 | SO687448 | LMP01 | Rahul Gupta | UERT10565 | Lakhimpur | 3MW | 9935096993 | Santosh Kumar Singh | VIKAS SHULKA | COMPLETED |  | 19.06.2018 | NOT PREPARED |  |  | #N/A
139 | 48016¦NBB01 | 07.06.2018 | 48016 | SO660942 | NBB01 | Rahul Gupta | UEGT13344 | Lakhimpur | MW | 9935096993 | Shakeel Mirza | VIKAS SHULKA | COMPLETED |  | 20.06.2018 | NOT PREPARED |  |  | #N/A
140 | 47530¦SWR01 | 17.05.2018 | 47530 |  | SWR01 | Rahul Gupta | UEGT11732 | Lakhimpur | EPM | 9935096993 | Shakeel Mirza | VIKAS SHULKA | COMPLETED |  | 20.06.2018 | NOT PREPARED |  |  | #N/A
141 | 47916¦ICH01 | 02.06.2018 | 47916 |  | ICH01 | Rahul Gupta | UEGT12213 | Lko Nsc | 3 EPM,MW IP55 & EW | 9935096993 | Ashish Kumar Singh | RAMESH | COMPLETED & EW pending |  | 20.06.2018 | NOT PREPARED |  |  | #N/A
142 | 48016¦ICH01 | 07.06.2018 | 48016 |  | ICH01 | Rahul Gupta | UEGT12213 | Lko Nsc | MW | 9935096993 | Ashish Kumar Singh | RAMESH | COMPLETED |  | 20.06.2018 | NOT PREPARED |  |  | #N/A
143 | 47938¦LKHD07 | 04.06.2018 | 47938 |  | LKHD07 | Rahul Gupta | UEGT10558 | Lko Nsc | MW | 9935096993 | Shiv Shankar | RAMESH | COMPLETED |  | 21.06.2018 | NOT PREPARED |  |  | #N/A
144 | 48016¦GEH01 | 07.06.2018 | 48016 |  | GEH01 | Rahul Gupta | UEGT11175 | Lko Nsc | MW | 9935096993 | Ritesh Tripathi | RAMESH | COMPLETED |  | 21.06.2018 | NOT PREPARED |  |  | #N/A
145 | 48172¦SDN01 | 21.06.2018 | 48172 |  | SDN01 | Shambhu Nath | UEGT10512 | Basti | CIVIL AC PAD | 9559961777 | PradeeP Kumar Mishra | Surrender TIWARI | COMPLETED |  | 21.06.2018 | PREPARED
146 | 47962¦MWQ01 | 05.06.2018 | 47962 |  | MWQ01 | Rahul Gupta | UEGT13091 | Lko Nsc | MW | 9935096993 | Sujeet Kumar Singh | RAMESH | COMPLETED |  | 22.06.2018 | NOT PREPARED |  |  | #N/A
147 | 48016¦MEY01 | 07.06.2018 | 48016 | SO693682 | MEY01 | Rahul Gupta | UEGT12327 | Lakhimpur | MW | 9935096993 | Upendra Kumar Dixit | VIKAS SHULKA | COMPLETED |  | 22.06.2018 | NOT PREPARED |  |  | #N/A
148 | 47938¦AUB01 | 04.06.2018 | 47938 | SO707394 | AUB01 | Rahul Gupta | UEGT11095 | Sitapur | 2MW | 9935096993 | Amit Kumar Mishra | VIKAS SHULKA | COMPLETED |  | 22.06.2018 | NOT PREPARED |  |  | #N/A
149 | 48016¦KUO01 | 07.06.2018 | 48016 | SO660907 | KUO01 | Rahul Gupta | UEGT10366 | Sitapur | 2 MW | 9935096993 | Pawan Kumar Mishra | VIKAS SHULKA | COMPLETED |  | 23.06.2018 | NOT PREPARED |  |  | #N/A
150 | 47938¦DLH01 | 04.06.2018 | 47938 | SO707400 | DLH01 | Rahul Gupta | UEGT12265 | Sitapur | 2MW | 9935096993 | Amit Kumar Mishra | VIKAS SHULKA | COMPLETED |  | 23.06.2018 | NOT PREPARED |  |  | #N/A
151 | 47735¦PWN01 | 28.05.2018 | 47735 |  | PWN01 | Shambhu Nath | UEGT12884 | Kushi Nagar | DISM. OF SMPS & PIU | 9559961777 | Animesh Kumar | SATYA PRAKASH | COMPLETED |  | 23.06.2018 | PREPARED |  |  | #N/A
152 | 47782¦PWN01 | 30.05.2018 | 47782 |  | PWN01 | Shambhu Nath | UEGT12884 | Kushi Nagar | EW | 9559961777 | Animesh Kumar | SATYA PRAKASH | COMPLETED |  | 23.06.2018 | PREPARED |  |  | #N/A
153 | 47962¦ITJ01 | 05.06.2018 | 47962 | SO676375 | ITJ01 | Rahul Gupta | UEGT11447 | Sitapur | MW | 9935096993 | Ratish Dev Shukla | VIKAS SHULKA | COMPLETED |  | 24.06.2018 | NOT PREPARED |  |  | #N/A
154 | 47938¦LKSH02 | 04.06.2018 | 47938 | SO706924 | LKSH02 | Rahul Gupta | UEGT10124 | Sitapur | MW | 9935096993 | Ratish Dev Shukla | VIKAS SHULKA | COMPLETED |  | 24.06.2018 | NOT PREPARED |  |  | #N/A
155 | 47916¦THO01 | 02.06.2018 | 47916 | SO706200 | THO01 | Rahul Gupta | UEGT12774 | Sitapur | 3 EPM,MW IP55 & EW | 9935096993 | Sanjiv Kumar Singh | VIKAS SHULKA | COMPLETED |  | 24.06.2018 | NOT PREPARED |  |  | #N/A
156 | 48016¦SHS01 | 07.06.2018 | 48016 | SO706926 | SHS01 | Rahul Gupta | UEGT12567 | Sitapur | MW | 9935096993 | Awatar Singh | VIKAS SHULKA | COMPLETED |  | 25.06.2018 | NOT PREPARED |  |  | #N/A
157 | 47868¦AHD01 | 31.05.2018 | 47868 |  | AHD01 | Shambhu Nath | UEGT11857 | Kushi Nagar | MW | 9559961777 | Ramesh ku. Gaur | DEEPAK SINGH | COMPLETED |  | 27.06.2018 | PREPARED |  |  | #N/A
158 | 47530¦BKY01 | 17.05.2018 | 47530 | SO678270 | BKY01 | Shambhu Nath | UEGT12182 | Mau | EPM | 9559961777 | Shantosh Singh | 35-0 | COMPLETED |  |  | NOT PREPARED |  |  | #N/A
159 | 47671¦JSK01 | 23.05.2018 | 47671 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | EW (37000) | Ran Vijay Singh | 9621827562 | SONU SINGH | COMPLETED |  | 04.07.2018 | NOT PREPARED |  |  | #N/A
160 | 48351¦JSK01 | 22.06.2018 | 48351 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | BB | Ran Vijay Singh | 9621827562 | SONU SINGH | COMPLETED |  |  | NOT PREPARED
161 | 47743¦KPT01 | 28.05.2018 | 47743 |  | KPT01 | Rahul Gupta | UEGT12670 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | Sunil Kumar Gupta | 9984999462 | ANOOP | COMPLETED |  | 04.07.2018 | NOT PREPARED |  |  | LTS/1819/0653
162 | 47743¦KRD01 | 28.05.2018 | 47743 |  | KRD01 | Rahul Gupta | UEGT12793 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | Ashutosh Kumar | 9794589276 | ANOOP | COMPLETED |  | 04.07.2018 | NOT PREPARED |  |  | #N/A
163 | 47743¦ABY01 | 28.05.2018 | 47743 |  | ABY01 | Rahul Gupta | UEGT12196 | Lakhimpur | CIVIL (1.2X1.2),EW,EPM,LADDER & PENDULUM | Shakeel Mirza | 8009937140 | ANOOP | COMPLETED |  | 04.07.2018 | NOT PREPARED |  |  | LTS/1819/0653
164 | 47029¦ZBR01 | 25.04.2018 | 47029 |  | ZBR01 | Rahul Gupta | UEGT13363 | Shahjahanpur | EW & BB | Manik Chandra | 7080861480 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
165 | 47671¦KRS01 | 23.05.2018 | 47671 |  | KRS01 | Rahul Gupta | UEGT10836 | Sitapur | MH,DIS. OF PIU,DIS. OF SMPS & EW | Dileep Kumar | 9839661597 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
166 | 47743¦SPW01 | 28.05.2018 | 47743 |  | SPW01 | Rahul Gupta | UEGT13410 | Sitapur | EPM | Vivek Singh | 9648010660 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
167 | 47938¦AKR01 | 04.06.2018 | 47938 | SO708838 | AKR01 | Rahul Gupta | UEGT11699 | Sitapur | MW | Surya Prakash Singh | 9956901615 | VIKASH SHUKLA | COMPLETED | 36-329 | 05.07.2018 | NOT PREPARED |  |  | #N/A
168 | 47916¦LKSH02 | 02.06.2018 | 47916 | SO706194 | LKSH02 | Rahul Gupta | UEGT10124 | Sitapur | 3 EPM,MW IP55 & EW | Ratish Dev Shukla | 9956167332 | VIKASH SHUKLA | COMPLETED | 40-1,90,170 | 05.07.2018 | NOT PREPARED |  |  | #N/A
169 | 48351¦KIM01 | 22.06.2018 | 48351 |  | KIM01 | Rahul Gupta | UEGT12153 | Lakhimpur | BB | Ashutosh Kumar | 9794589276 | VIKASH SHUKLA | COMPLETED |  | 05.07.2018 | NOT PREPARED
170 | 48351¦ABY01 | 22.06.2018 | 48351 |  | ABY01 | Rahul Gupta | UEGT12196 | Lakhimpur | BB | Shakeel Mirza | 8009937140 | ANOOP | COMPLETED |  | 05.07.2018 | NOT PREPARED
171 | 48351¦STSH04 | 22.06.2018 | 48351 |  | STSH04 | Rahul Gupta | UEGT10605 | Lakhimpur | BB | Ashutosh Kumar | 9794589276 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED
172 | 48351¦PTI01 | 22.06.2018 | 48351 |  | PTI01 | Rahul Gupta | UEGT11666 | Lakhimpur | BB | Mohd. Shahid Khan | 7081990896 | SATYA PRAKASH | COMPLETED |  | 05.07.2018 | NOT PREPARED
173 | 47938¦BRL01 | 04.06.2018 | 47938 |  | BRL01 | Rahul Gupta | UEGT11710 | Shahjahanpur | EW | Anshul Mishra | 9648399609 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
174 | 48130¦NWA01 | 14.06.2018 | 48130 |  | NWA01 | Rahul Gupta | UEGT11748 | Lko Nsc | 3MW | Imran Khan | 9795281428 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
175 | 48130¦RXM01 | 14.06.2018 | 48130 |  | RXM01 | Rahul Gupta | UEGT13522 | Lko Nsc | 2MW | Imran Khan | 9795281428 | VIKAS SHULKA | COMPLETED |  | 05.07.2018 | NOT PREPARED |  |  | #N/A
176 | 47962¦MHD01 | 05.06.2018 | 47962 |  | MHD01 | Rahul Gupta | UEGT10519 | Shahjahanpur | MW | Anshul Mishra | 9648399609 | VIKASH SHUKLA | COMPLETED | 18-45 | 05.07.2018 | NOT PREPARED |  |  | #N/A
177 | 48016¦SUZ01 | 07.06.2018 | 48016 |  | SUZ01 | Rahul Gupta | UEGT12888 | Shahjahanpur | MW | OM Prakash Singh | 9919901002 | VIKASH SHUKLA | COMPLETED | 39-333 | 05.07.2018 | NOT PREPARED |  |  | #N/A
178 | 48016¦KMX01 | 07.06.2018 | 48016 |  | KMX01 | Rahul Gupta | UEGT12993 | Shahjahanpur | MW | OM Prakash Singh | 9919901002 | VIKASH SHUKLA | COMPLETED | 38-235 | 05.07.2018 | NOT PREPARED |  |  | #N/A
179 | 48130¦KDG01 | 14.06.2018 | 48130 |  | KDG01 | Rahul Gupta | UEGT10811 | Shahjahanpur | MW | Praveen Kumar Yadav | 9721611872 | VIKASH SHUKLA | COMPLETED | 35-140 | 06.07.2018 | NOT PREPARED |  |  | #N/A
180 | 47671¦PMP01 | 23.05.2018 | 47671 |  | PMP01 | Jitender Chaturvedi | UEGT13419 | Gonda | EW (29000) | Ram Swaraj Verma | 9956756199 | other company | COMPLETED |  | 06.07.2018 | NOT PREPARED |  |  | #N/A
181 | 47023¦GTN01 | 25.4.2018 | 47023 |  | GTN01 | Rahul Gupta | UEGT11597 | Lakhimpur | MW | Mukesh Kumar Mishra | 8052056483 | VIKASH SHUKLA | COMPLETED |  | 07.07.2018 | NOT PREPARED |  |  | LTS/1819/0643
182 | 48222¦KME01 | 18.06.2014 | 48222 |  | KME01 | Rahul Gupta | UEGT11664 | Lko Nsc | EPM | Ran Vijay Singh | 9621827562 | VIKASH SHUKLA | COMPLETED |  | 07.07.2018 | NOT PREPARED
183 | 48222¦JSK01 | 18.06.2014 | 48222 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | 2EPM | Ran Vijay Singh | 9621827562 | VIKASH SHUKLA | COMPLETED |  | 08.07.2018 | NOT PREPARED
184 | 48529¦MMK01 | 02.07.2018 | 48529 |  | MMK01 | Rahul Gupta | UEGT11654 | Sitapur | MW | Vivek Singh | 9648010660 | VIKASH SHUKLA | COMPLETED |  | 11.07.2018 | NOT PREPARED
185 | 48529¦GMQ01 | 02.07.2018 | 48529 |  | GMQ01 | Rahul Gupta | UEGT13044 | Sitapur | MW | Vivek Singh | 9648010660 | VIKASH SHUKLA | COMPLETED |  | 11.07.2018 | NOT PREPARED
186 | 48529¦CHP01 | 02.07.2018 | 48529 |  | CHP01 | Rahul Gupta | UEGT12226 | Sitapur | 2MW | Vivek Singh | 9648010660 | VIKASH SHUKLA | COMPLETED |  | 11.07.2018 | NOT PREPARED
187 | 48572¦GDE01 | 03.07.2018 | 48572 |  | GDE01 | Rahul Gupta | UEGT11089 | Sitapur | 2MW | Vivek Singh | 9648010660 | VIKASH SHUKLA | COMPLETED |  | 11.07.2018 | NOT PREPARED

## HOLD-PO CLOSED SHEET
SL. NO. | HELPER | PO DATE | PO NO. | SO. NO. | SITE ID | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | VENDOR' NAME | STATUS | SITE ALLOTTED BY | COMPLETION DATE | JMR STATUS
1 | 46924¦GKP20 | 19.04.2018 | 46924 | SO601795 | GKP20 | UEGT10726 | 9559196316 | MW | 9559961777 | Chandrajeet PrataP Singh |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
2 | 46924¦GKP12 | 19.04.2018 | 46924 | SO600980 | GKP12 | UERT10170 | 9559196316 | 3MW | 9559961777 | Harish Chandra |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
3 | 46924¦GKP22 | 19.04.2018 | 46924 | SO601515 | GKP22 | UEGT10478 | 9559196316 | MW | 9559961777 | Harish Chandra |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
4 | 46924¦GKP04 | 19.04.2018 | 46924 | SO601232 | GKP04 | UEGT10013 | 9559196316 | 2MW | 9559961777 | Raghvendra Kumar Gautum |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
5 | 46924¦GKP33 | 19.04.2018 | 46924 | SO601797 | GKP33 | UEGT10883 | 9559196316 | MW | 9559961777 | Dharmendra Pandey |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
6 | 46924¦GKP39 | 19.04.2018 | 46924 | SO601773 | GKP39 | UEGT11178 | 9559196316 | MW | 9559961777 | Harish Chandra |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
7 | 46924¦GKP48 | 19.04.2018 | 46924 | SO601501 | GKP48 | UERT10906 | 9559196316 | MW | 9559961777 | Chandrajeet PrataP Singh |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
8 | 46924¦GKP16 | 19.04.2018 | 46924 | SO601495 | GKP16 | UEGT10331 | 9559196316 | MW | 9559961777 | Dharmendra Pandey |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
9 | 46924¦GKP66 | 19.04.2018 | 46924 | SO601509 | GKP66 | UERP12575 | 9559196316 | MW | 9559961777 | Harish Chandra |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
11 | 47002¦RDP01 | 24.04.2018 | 47002 | SO682366 | RDP01 | UEGT10488 | 9559196316 | EW & TRANSMISSION RACK | 9559961777 | Ram Prakash Singh |  | space not available for hanging shambhu sir said 1 hang only NO NEED OF WORK SAID BY SHAMBHU SIR |  |  |  | #N/A
13 | 47027¦GKP27 | 25.04.2018 | 47027 | SO662747 | GKP27 | UEGT10898 | 9559196316 | MW | 9559961777 | Chandrajeet PrataP Singh |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
16 | 47469¦GKP41 | 15.05.2018 | 47469 | SO685496 | GKP41 | UERT10770 | 9559196316 | MW IP55 | 9559961777 | Dharmendra Pandey |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
20 | 47602¦DMN01 | 21.05.2018 | 47602 |  | DMN01 | UEGT12708 | 9559196318 | EW | 9559196969 | Abhinendra Chaube |  | PO LINE CLOSED |  |  |  | #N/A
21 | 47602¦NYU01 | 21.05.2018 | 47602 |  | NYU01 | UEGT12639 | 9559196318 | EW (29000) | 9559196969 | Amit Kumar Pandey |  | PO LINE CLOSED |  |  |  | #N/A
22 | 47602¦MPU01 | 21.05.2018 | 47602 |  | MPU01 | UEGT11769 | 9559196318 | 3EPM | 9559196969 | Vivek Tiwari |  | PO LINE CLOSED |  |  |  | #N/A
25 | 47670¦VNS09 | 23.05.2018 | 47670 |  | VNS09 | UERT10107 | 9559196318 | MW | 9559196969 | Pradeep Kumar Saini |  | OWNER ISSUE |  |  |  | #N/A
37 | 47742¦KYA01 | 28.05.2018 | 47742 |  | KYA01 | UEGT12059 | 9559196316 | MW | 9559961777 | Satya Kumar Shukla |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
38 | 47742¦GKP07 | 28.05.2018 | 47742 |  | GKP07 | UERT10113 | 9559196316 | 3EPM | 9559961777 | Raghvendra Kumar Gautum |  | HOLD BY SHAMBHU SIR |  |  |  | #N/A
8 | 47670¦PDV01 | 23.05.2018 | 47670 |  | PDV01 | Dharmbir | UERT13320 | Varanasi | MW | Vivek Pratap Singh | 9651353444 | PO CLOSED |  |  |  |  | #N/A
9 | 47670¦SRY02 | 23.05.2018 | 47670 |  | SRY02 | Dharmbir | UEGT13547 | Mirzapur | MW | Inderjeet Pathak | 9451515154 | PO CLOSED |  |  |  |  | #N/A
10 | 47670¦JGP01 | 23.05.2018 | 47670 |  | JGP01 | Dharmbir | UEGT11551 | Mirzapur | MW | Sujeet Pandey | 9839958356 | PO CLOSED |  |  |  |  | #N/A

## Sheet2
AHD01 | UEGT11857 | 9559196316 | MW | 9559961777 | Ramesh ku. Gaur | 32-263
BCG01 | UEGT13383 | 9559196316 | MW IP55 & EW | 9559961777 | Santosh Kumar Yadav
PO DATE | PO NO. | SITE ID | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No.
15.05.2018 | 47471 | ARJ01 | UEGT11119 | Deoria | CIVIL (1.2X1.2),EW & MH | GoPal Mishra | 9935599812
15.05.2018 | 47469 | BCG01 | UEGT13383 | Maharajganj | EW | Santosh Kumar Yadav | 9956290322 | 5500
23.05.2018 | 47671 | DBH01 | UEGT12186 | Mau | CIVIL (1.2X1.2),EW & MH | Shantosh Singh | 9628507454
| 46108/40637 | BEI01 | UEGT13378 | 9559196316 | PP | Surendra Kumar Tripathi | 9792992998
| 45980 | GBZ01 | UEGT10697 | 9559196316 | T/RACK | Deepak Kumar singh | 9452382214 | FINALLY CLOSED
PO DATE | PO NO. | SO. NO. | SITE ID | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | Status
25.06.2018 | 48380 |  | DBD01 | UEGT12470 | Basti | EW & BB | Arun Kumar TriPathi | 9984543050 | Material Not Avilable
15.05.2018 | 47471 | SO697099 | ARJ01 | UEGT11119 | Deoria | CIVIL (1.2X1.2),EW & MH | GoPal Mishra | 9935599812 | Done
23.05.2018 | 47671 | SO685394 | NGP01 | UEGT11257 | Deoria | EW | Sanjog Ku.Singh | 8052267418 | Done
21.06.2018 | 48333 |  | KPB01 | UEGT12560 | Deoria | EPM | Sher Bahadur Singh | 8948600632 | Material Not Avilable
21.06.2018 | 48333 |  | SSY01 | UEGT13327 | Deoria | EPM | Sher Bahadur Singh | 8948600632 | Material Not Avilable
22.06.2018 | 48351 |  | SSY01 | UEGT13327 | Deoria | BB | Sher Bahadur Singh | 8948600632 | Material Not Avilable
28.05.2018 | 47735 |  | HSW01 | UEGT11076 | Gorakhpur | DISM. OF SMPS & PIU | Dharmendra Pandey | 9956133918 | Done
22.06.2018 | 48351 |  | GKP41 | UERT10770 | Gorakhpur | BB | Dharmendra Pandey | 9956133918 | Material Not Avilable
21.06.2018 | 48333 |  | SEW01 | UEGT10740 | Kushi Nagar | CIVIL (1.2X1.2),LADDER,PENDULUM,EPM,MW IP55,EW & MH | Ramesh ku. Gaur | 9838106014 | Material Not Avilable
22.06.2018 | 48351 |  | PGH01 | UEGT11709 | Kushi Nagar | BB | Ramesh ku. Gaur | 9838106014 | Done
25.06.2018 | 48380 |  | CHS01 | UEGT11752 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014 | Material Not Avilable
25.06.2018 | 48380 |  | SZR01 | UEGT13279 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014 | Material Not Avilable
25.06.2018 | 48380 |  | BIO01 | UEGT12009 | Kushi Nagar | EW & BB | Susheel Kumar | 9198010591 | Material Not Avilable
22.06.2018 | 48351 |  | SRH01 | UEGT11338 | Maharajganj | BB | Harendra Kumar Patel | 9198673400 | Done
15.05.2018 | 47469 | SO689006 | DBH01 | UEGT12186 | Mau | 3 EPM & MW IP55 | Shantosh Singh | 9628507454 | WIP
23.05.2018 | 47671 | SO689006 | DBH01 | UEGT12186 | Mau | CIVIL (1.2X1.2),EW & MH | Shantosh Singh | 9628507454 | WIP
21.06.2018 | 48333 |  | BHO01 | UEGT11778 | Mau | MW | Ashok Kumar Vishwkarma | 9839316559 | Material Not Avilable
21.06.2018 | 48333 |  | GKVN11 | UEGT10257 | Mau | MW | Akhilesh Singh | 9936639664 | Material Not Avilable
21.06.2018 | 48333 |  | KZG01 | UEGT13139 | Mau | EPM | Sanjay Kumar Singh | 9648887413 | Material Not Avilable
22.06.2018 | 48351 |  | DBH01 | UEGT12186 | Mau | BB | Shantosh Singh | 9628507454 | Material Not Avilable
25.06.2018 | 48380 |  | SWM01 | UEGT12742 | Mau | EW & BB | Amit Kumar Srivastava | 8115563289 | Material Not Avilable
PO DATE | PO NO. | SO. NO. | SITE ID | ZDM | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | Status
21.06.2018 | 48333 |  | GKVN11 | Shambhu Nath | UEGT10257 | Mau | MW | Akhilesh Singh | 9936639664 | material not available
03.07.2018 | 48572 |  | REU01 | Rahul Gupta | UEGT10985 | Sitapur | MW | Amit Singh | 9936966940 | material not available
21.06.2018 | 48333 |  | BHO01 | Shambhu Nath | UEGT11778 | Mau | MW | Ashok Kumar Vishwkarma | 9839316559 | material not available
02.07.2018 | 48529 |  | ADD01 | Shambhu Nath | UEGT13176 | Mau | MW | Dhanjay Verma | 9795431482 | yes
22.06.2018 | 48351 |  | GKP41 | Shambhu Nath | UERT10770 | Gorakhpur | BB | Dharmendra Pandey | 9956133918 | material not available
22.06.2018 | 48351 |  | SRH01 | Shambhu Nath | UEGT11338 | Maharajganj | BB | Harendra Kumar Patel | 9198673400 | done
18.06.2014 | 48222 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EPM | Harvansh Mani Tripathi | 9565065366 | material not available
03.07.2018 | 48572 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | MW | Manik Chandra | 7080861480 | material not available
15.06.2014 | 48186 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | BB | Mohd. Shahid Khan | 7081990896 | material not available
18.06.2014 | 48222 |  | HZD01 | Rahul Gupta | UEGT13024 | Lakhimpur | 3EPM | Mohd. Shahid Khan | 7081990896 | material not available
25.4.2018 | 47023 |  | GTN01 | Rahul Gupta | UEGT11597 | Lakhimpur | MW | Mukesh Kumar Mishra | 8052056483 | done
02.07.2018 | 48529 |  | SHA03 | Rahul Gupta | UEGT10273 | Shahjahanpur | 2MW | OM Prakash Singh | 9919901002 | material not available
02.07.2018 | 48529 |  | KDZ01 | Rahul Gupta | UEGT13356 | Shahjahanpur | 3MW | Praveen Kumar Yadav | 9721611872 | yes
07.06.2018 | 48016 |  | LKSH10 | Rahul Gupta | UEGT10497 | Shahjahanpur | MW | Raghuveer Singh Yadav | 9792469268 | material not available
18.06.2014 | 48222 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | 2MW | Ram Lakhan | 9621911073 | material not available
18.06.2014 | 48222 |  | KAC01 | Rahul Gupta | UEGT10976 | Sitapur | 2MW | Ram Lakhan | 9621911073 | material not available
18.06.2014 | 48222 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | EPM | Ram Lakhan | 9621911073 | material not available
02.07.2018 | 48529 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | MW | Ram Lakhan | 9621911073 | material not available
02.07.2018 | 48529 |  | KZU01 | Rahul Gupta | UEGT11741 | Sitapur | 2MW | Ram Lakhan | 9621911073 | material not available
02.07.2018 | 48529 |  | STP05 | Rahul Gupta | UEGT10891 | Sitapur | 2MW | Ram Lakhan | 9621911073 | material not available
22.06.2018 | 48351 |  | PGH01 | Shambhu Nath | UEGT11709 | Kushi Nagar | BB | Ramesh ku. Gaur | 9838106014 | done
07.06.2018 | 48016 |  | LKVN03 | Rahul Gupta | UEGT10138 | Lko Nsc | MW | Ran Vijay Singh | 9621827562 | material not available
18.06.2014 | 48222 |  | KME01 | Rahul Gupta | UEGT11664 | Lko Nsc | EPM | Ran Vijay Singh | 9621827562 | done
18.06.2014 | 48222 |  | JSK01 | Rahul Gupta | UEGT11525 | Lko Nsc | 2EPM | Ran Vijay Singh | 9621827562 | done
02.07.2018 | 48529 |  | LKSH03 | Rahul Gupta | UEGT10121 | Sitapur | MW | Ratish Dev Shukla | 9956167332 | done
02.07.2018 | 48529 |  | LKSH01 | Rahul Gupta | UEGT10086 | Sitapur | MW | Ratish Dev Shukla | 9956167332 | done
21.06.2018 | 48333 |  | KZG01 | Shambhu Nath | UEGT13139 | Mau | EPM | Sanjay Kumar Singh | 9648887413 | material not available
18.06.2014 | 48222 |  | LMP02 | Rahul Gupta | UEGT10567 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 | material not available
18.06.2014 | 48222 |  | KHR01 | Rahul Gupta | UEGT10662 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222 | material not available
02.07.2018 | 48529 |  | BET01 | Shambhu Nath | UEGT12437 | Gorakhpur | 2MW | Satya Prakash Singh | 7317503030 | material not available
03.07.2018 | 48572 |  | BPO01 | Rahul Gupta | UEGT12206 | Lakhimpur | MW | Shakeel Mirza | 8009937140 | material not available
15.05.2018 | 47469 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | 3 EPM & MW IP55 | Shantosh Singh | 9628507454 | material not available
22.06.2018 | 48351 |  | DBH01 | Shambhu Nath | UEGT12186 | Mau | BB | Shantosh Singh | 9628507454 | material not available
21.06.2018 | 48333 |  | KPB01 | Shambhu Nath | UEGT12560 | Deoria | EPM | Sher Bahadur Singh | 8948600632 | material not available
21.06.2018 | 48333 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | EPM | Sher Bahadur Singh | 8948600632 | yes
22.06.2018 | 48351 |  | SSY01 | Shambhu Nath | UEGT13327 | Deoria | BB | Sher Bahadur Singh | 8948600632 | material not available
03.07.2018 | 48572 |  | ADH01 | Rahul Gupta | UEGT11652 | Lko Nsc | MW | Shiv Shankar | 9936028884 | yes
28.05.2018 | 47743 |  | MAL01 | Rahul Gupta | UEGT10545 | Lko Nsc | 2EPM | Sujeet Kumar Singh | 9936996735 | yes
18.06.2014 | 48222 |  | MWQ01 | Rahul Gupta | UEGT13091 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735 | yes
02.07.2018 | 48529 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735 | material not available
03.07.2018 | 48572 |  | JTH01 | Rahul Gupta | UEGT12390 | Lakhimpur | MW | Sunil Kumar Gupta | 9984999462 | material not available
02.07.2018 | 48529 |  | DMR01 | Shambhu Nath | UEGT10615 | Basti | MW | Surendra Kumar Tripathi | 9792992998 | material not available
02.07.2018 | 48529 |  | LAH01 | Rahul Gupta | UEGT10608 | Sitapur | MW | Surya Prakash Singh | 9956901615 | material not available
18.06.2014 | 48222 |  | CDP01 | Rahul Gupta | UEGT12149 | Lakhimpur | EPM | Upendra Kumar Dixit | 9839212570 | material not available
02.07.2018 | 48529 |  | MMK01 | Rahul Gupta | UEGT11654 | Sitapur | MW | Vivek Singh | 9648010660 | yes
02.07.2018 | 48529 |  | GMQ01 | Rahul Gupta | UEGT13044 | Sitapur | MW | Vivek Singh | 9648010660 | yes
02.07.2018 | 48529 |  | CHP01 | Rahul Gupta | UEGT12226 | Sitapur | 2MW | Vivek Singh | 9648010660 | yes
03.07.2018 | 48572 |  | GDE01 | Rahul Gupta | UEGT11089 | Sitapur | 2MW | Vivek Singh | 9648010660 | yes