## Sheet1
SL. NO. | HELPER | PO DATE | PO NO | SO. NO | SITE ID | ZDM | INFRATEL ID | LOCATION | WORK TYPE | Tech. Name | Tech. No. | VENDOR' NAME | STATUS | SITE ALLOTTED BY | COMPLETION DATE | JMR STATUS
1 | 46883¦KWL01 | 19.04.2018 | 46883 |  | KWL01 | Rahul Gupta | UEGT11970 | Lko Nsc | CIVIL(1.2X1.2), EW, BB & MH | Pawan Pratap Singh | 9935985000
2 | 47471¦ARJ01 | 15.05.2018 | 47471 | SO697099 | ARJ01 | Shambhu Nath | UEGT11119 | Deoria | CIVIL (1.2X1.2),EW & MH | GoPal Mishra | 9935599812
3 | 47469¦DBH01 | 15.05.2018 | 47469 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | 3 EPM & MW IP55 | Shantosh Singh | 9628507454
4 | 47602¦DFP01 | 21.05.2018 | 47602 |  | DFP01 | Rahul Gupta | UEGT11875 | Sitapur | EW | Dileep Kumar | 9839661597
5 | 47653¦Construction of New Gorakhpur Zonal Office | 24.05.2018 | 47653 |  | Construction of New Gorakhpur Zonal Office | Shambhu Nath | #N/A | #N/A | Construction of New Gorakhpur Zonal Office | #N/A | #N/A
6 | 47671¦DBH01 | 23.05.2018 | 47671 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | CIVIL (1.2X1.2),EW & MH | Shantosh Singh | 9628507454
7 | 47671¦NGP01 | 23.05.2018 | 47671 | SO685394 | NGP01 | Shambhu Nath | UEGT11257 | Deoria | EW | Sanjog Ku.Singh | 8052267418
8 | 47735¦HSW01 | 28.05.2018 | 47735 |  | HSW01 | Shambhu Nath | UEGT11076 | Gorakhpur | DISM. OF SMPS & PIU | Dharmendra Pandey | 9956133918
9 | 47916¦PTI01 | 02.06.2018 | 47916 |  | PTI01 | Rahul Gupta | UEGT11666 | Lakhimpur | 3 EPM,MW IP55 & EW | Mohd. Shahid Khan | 7081990896
10 | 47916¦GLK01 | 02.06.2018 | 47916 | SO680093 | GLK01 | Rahul Gupta | UEGT10978 | Sitapur | 3 EPM,MW IP55 & EW | Amit Singh | 9936966940
11 | 47916¦ENG01 | 02.06.2018 | 47916 | SO705974 | ENG01 | Rahul Gupta | UEGT12301 | Sitapur | 3 EPM,MW IP55 & EW | Pawan Kumar Mishra | 9956493163
12 | 48016¦LKSH10 | 07.06.2018 | 48016 |  | LKSH10 | Rahul Gupta | UEGT10497 | Shahjahanpur | MW | Raghuveer Singh Yadav | 9792469268
13 | 47916¦SAL01 | 02.06.2018 | 47916 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | 3 EPM,MW IP55 & EW | Ram Lakhan | 9621911073
14 | 48016¦LKVN03 | 07.06.2018 | 48016 |  | LKVN03 | Rahul Gupta | UEGT10138 | Lko Nsc | MW | Ran Vijay Singh | 9621827562
15 | 48071¦GPY01 | 11.06.2018 | 48071 |  | GPY01 | Rahul Gupta | UEGT12298 | Lakhimpur | EW | Harvansh Mani Tripathi | 9565065366
16 | 48130¦BNV01 | 14.06.2018 | 48130 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | EW | Mohd. Shahid Khan | 7081990896
17 | 48184¦LUK06 | 15.06.2014 | 48184 |  | LUK06 | Rahul Gupta | UERT10193 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Mangla Prasad | 8738888044
18 | 48184¦LUK05 | 15.06.2014 | 48184 |  | LUK05 | Rahul Gupta | UERT10053 | Lko Scs | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Dhirendra Pratap Singh | 9794704349
19 | 48184¦LUK112 | 15.06.2014 | 48184 |  | LUK112 | Rahul Gupta | UERT10856 | Lko Scn | CIVIL (1.2X1.2),LADDER,PENDULUM,EW & MH | Ashutosh Kumar | 7607094484/9794999531
20 | 48186¦BNV01 | 15.06.2014 | 48186 |  | BNV01 | Rahul Gupta | UEGT12891 | Lakhimpur | BB | Mohd. Shahid Khan | 7081990896
21 | 48222¦LMP02 | 18.06.2014 | 48222 |  | LMP02 | Rahul Gupta | UEGT10567 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222
22 | 48222¦KHR01 | 18.06.2014 | 48222 |  | KHR01 | Rahul Gupta | UEGT10662 | Lakhimpur | MW | Santosh Kumar Singh | 9838357222
23 | 48222¦BXS01 | 18.06.2014 | 48222 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | 2MW | Ram Lakhan | 9621911073
24 | 48222¦KAC01 | 18.06.2014 | 48222 |  | KAC01 | Rahul Gupta | UEGT10976 | Sitapur | 2MW | Ram Lakhan | 9621911073
25 | 48222¦MWQ01 | 18.06.2014 | 48222 |  | MWQ01 | Rahul Gupta | UEGT13091 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735
26 | 48222¦HZD01 | 18.06.2014 | 48222 |  | HZD01 | Rahul Gupta | UEGT13024 | Lakhimpur | 3EPM | Mohd. Shahid Khan | 7081990896
27 | 48222¦MJA01 | 18.06.2014 | 48222 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EPM | Harvansh Mani Tripathi | 9565065366
28 | 48222¦CDP01 | 18.06.2014 | 48222 |  | CDP01 | Rahul Gupta | UEGT12149 | Lakhimpur | EPM | Upendra Kumar Dixit | 9839212570
29 | 48222¦SAL01 | 18.06.2014 | 48222 |  | SAL01 | Rahul Gupta | UEGT11948 | Sitapur | EPM | Ram Lakhan | 9621911073
30 | 48333¦BHO01 | 21.06.2018 | 48333 | SO689904 | BHO01 | Shambhu Nath | UEGT11778 | Mau | MW | Ashok Kumar Vishwkarma | 9839316559
31 | 48333¦GKVN11 | 21.06.2018 | 48333 | SO690519 | GKVN11 | Shambhu Nath | UEGT10257 | Mau | MW | Akhilesh Singh | 9936639664
32 | 48333¦KPB01 | 21.06.2018 | 48333 | SO725616 | KPB01 | Shambhu Nath | UEGT12560 | Deoria | EPM | Sher Bahadur Singh | 8948600632
33 | 48333¦SSY01 | 21.06.2018 | 48333 | SO719921 | SSY01 | Shambhu Nath | UEGT13327 | Deoria | EPM | Sher Bahadur Singh | 8948600632
34 | 48333¦KZG01 | 21.06.2018 | 48333 | SO722686 | KZG01 | Shambhu Nath | UEGT13139 | Mau | EPM | Sanjay Kumar Singh | 9648887413
35 | 48351¦SSY01 | 22.06.2018 | 48351 | SO666491 | SSY01 | Shambhu Nath | UEGT13327 | Deoria | BB | Sher Bahadur Singh | 8948600632
36 | 48351¦PGH01 | 22.06.2018 | 48351 | SO679988 | PGH01 | Shambhu Nath | UEGT11709 | Kushi Nagar | BB | Ramesh ku. Gaur | 9838106014
37 | 48351¦SRH01 | 22.06.2018 | 48351 | SO684321 | SRH01 | Shambhu Nath | UEGT11338 | Maharajganj | BB | Harendra Kumar Patel | 9198673400
38 | 48351¦GKP41 | 22.06.2018 | 48351 | SO685496 | GKP41 | Shambhu Nath | UERT10770 | Gorakhpur | BB | Dharmendra Pandey | 9956133918
39 | 48351¦DBH01 | 22.06.2018 | 48351 | SO689006 | DBH01 | Shambhu Nath | UEGT12186 | Mau | BB | Shantosh Singh | 9628507454
40 | 48380¦CHS01 | 25.06.2018 | 48380 | SO669149 | CHS01 | Shambhu Nath | UEGT11752 | Kushi Nagar | EW & BB | Ramesh ku. Gaur | 9838106014
41 | 48380¦SWM01 | 25.06.2018 | 48380 | SO667224 | SWM01 | Shambhu Nath | UEGT12742 | Mau | EW & BB | Amit Kumar Srivastava | 8115563289
42 | 48380¦BIO01 | 25.06.2018 | 48380 | SO668094 | BIO01 | Shambhu Nath | UEGT12009 | Kushi Nagar | EW & BB | Susheel Kumar | 9198010591
43 | 48380¦DBD01 | 25.06.2018 | 48380 | SO666042 | DBD01 | Shambhu Nath | UEGT12470 | Basti | EW & BB | Arun Kumar TriPathi | 9984543050
44 | 48529¦ADD01 | 02.07.2018 | 48529 |  | ADD01 | Shambhu Nath | UEGT13176 | Mau | MW | Dhanjay Verma | 9795431482
45 | 48529¦SHA03 | 02.07.2018 | 48529 |  | SHA03 | Rahul Gupta | UEGT10273 | Shahjahanpur | 2MW | OM Prakash Singh | 9919901002
46 | 48529¦LKSH03 | 02.07.2018 | 48529 |  | LKSH03 | Rahul Gupta | UEGT10121 | Sitapur | MW | Ratish Dev Shukla | 9956167332
47 | 48529¦LKSH01 | 02.07.2018 | 48529 |  | LKSH01 | Rahul Gupta | UEGT10086 | Sitapur | MW | Ratish Dev Shukla | 9956167332
48 | 48529¦LAH01 | 02.07.2018 | 48529 |  | LAH01 | Rahul Gupta | UEGT10608 | Sitapur | MW | Surya Prakash Singh | 9956901615
49 | 48529¦DMR01 | 02.07.2018 | 48529 | SO689981 | DMR01 | Shambhu Nath | UEGT10615 | Basti | MW | Surendra Kumar Tripathi | 9792992998
50 | 48529¦BXS01 | 02.07.2018 | 48529 |  | BXS01 | Rahul Gupta | UEGT13455 | Sitapur | MW | Ram Lakhan | 9621911073
51 | 48529¦KZU01 | 02.07.2018 | 48529 |  | KZU01 | Rahul Gupta | UEGT11741 | Sitapur | 2MW | Ram Lakhan | 9621911073
52 | 48529¦KDZ01 | 02.07.2018 | 48529 |  | KDZ01 | Rahul Gupta | UEGT13356 | Shahjahanpur | 3MW | Praveen Kumar Yadav | 9721611872
53 | 48529¦STP05 | 02.07.2018 | 48529 |  | STP05 | Rahul Gupta | UEGT10891 | Sitapur | 2MW | Ram Lakhan | 9621911073
54 | 48529¦BET01 | 02.07.2018 | 48529 | SO716700 | BET01 | Shambhu Nath | UEGT12437 | Gorakhpur | 2MW | Satya Prakash Singh | 7317503030
55 | 48529¦BGZ01 | 02.07.2018 | 48529 |  | BGZ01 | Rahul Gupta | UEGT12751 | Lko Nsc | 2MW | Sujeet Kumar Singh | 9936996735
56 | 48572¦BPO01 | 03.07.2018 | 48572 |  | BPO01 | Rahul Gupta | UEGT12206 | Lakhimpur | MW | Shakeel Mirza | 8009937140
57 | 48572¦LKSH08 | 03.07.2018 | 48572 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | MW | Manik Chandra | 7080861480
58 | 48572¦ADH01 | 03.07.2018 | 48572 |  | ADH01 | Rahul Gupta | UEGT11652 | Lko Nsc | MW | Shiv Shankar | 9936028884
59 | 48572¦JTH01 | 03.07.2018 | 48572 |  | JTH01 | Rahul Gupta | UEGT12390 | Lakhimpur | MW | Sunil Kumar Gupta | 9984999462
60 | 48572¦REU01 | 03.07.2018 | 48572 |  | REU01 | Rahul Gupta | UEGT10985 | Sitapur | MW | Amit Singh | 9936966940
61 | 48649¦CBD01 | 06.07.2018 | 48649 |  | CBD01 | Rahul Gupta | UEGT13393 | Shahjahanpur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Praveen Kumar Yadav | 9721611872
62 | 48649¦LKSH08 | 06.07.2018 | 48649 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | EW, EPM, GROUTING OF PANDULAM, LADDER | Manik Chandra | 7080861480
63 | 48649¦LKSH04 | 06.07.2018 | 48649 |  | LKSH04 | Rahul Gupta | UEGT10125 | Sitapur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Pawan Kumar Mishra | 9956493163
64 | 48649¦DMZ01 | 06.07.2018 | 48649 |  | DMZ01 | Rahul Gupta | UEGT13021 | Sitapur | EW, EPM, GROUTING OF PANDULAM, LADDER | Awatar Singh | 9984496285
65 | 48649¦KNSH09 | 06.07.2018 | 48649 |  | KNSH09 | Rahul Gupta | UEGT10447 | Shahjahanpur | EW, 4EPM, GROUTING OF PANDULAM, LADDER | OM Prakash Singh | 9919901002
66 | 48649¦BRM01 | 06.07.2018 | 48649 |  | BRM01 | Rahul Gupta | UEGT12356 | Sitapur | EW, 2EPM, GROUTING OF PANDULAM, LADDER | Pawan Kumar Mishra | 9956493163
67 | 48649¦AUB01 | 06.07.2018 | 48649 |  | AUB01 | Rahul Gupta | UEGT11095 | Sitapur | EW, GROUTING OF PANDULAM, LADDER | Amit Kumar Mishra | 9648474341
68 | 48649¦AJP01 | 06.07.2018 | 48649 |  | AJP01 | Rahul Gupta | UEGT11100 | Sitapur | T/RACK & EW | Amit Singh | 9936966940
69 | 48649¦MOO01 | 06.07.2018 | 48649 |  | MOO01 | Rahul Gupta | UEGT13209 | Sitapur | T/RACK & EW | Amit Singh | 9936966940
70 | 48649¦LUK222 | 06.07.2018 | 48649 |  | LUK222 | Rahul Gupta | UERT11681 | Lko Scs | MW IP 55 & EW | Sarvesh Kumar | 9936309777
71 | 48649¦LUK147 | 06.07.2018 | 48649 |  | LUK147 | Rahul Gupta | UERT11490 | Lko Scn | EW, MH, LADDER & PANDULAM | Sachin Tomar | 9758655572
72 | 48649¦MJA01 | 06.07.2018 | 48649 |  | MJA01 | Rahul Gupta | UEGT12391 | Lakhimpur | EW, BB & EPM | Harvansh Mani Tripathi | 9565065366
73 | 48724¦LUK147 | 10.07.2018 | 48724 |  | LUK147 | Rahul Gupta | UERT11490 | Lko Scn | CIVIL (1.2X1.2) | Sachin Tomar | 9758655572
74 | 48724¦CBD01 | 10.07.2018 | 48724 |  | CBD01 | Rahul Gupta | UEGT13393 | Shahjahanpur | CIVIL (1.2X1.2) | Praveen Kumar Yadav | 9721611872
75 | 48724¦LKSH08 | 10.07.2018 | 48724 |  | LKSH08 | Rahul Gupta | UEGT10262 | Shahjahanpur | CIVIL (1.2X1.2) | Manik Chandra | 7080861480
76 | 48724¦LKSH04 | 10.07.2018 | 48724 |  | LKSH04 | Rahul Gupta | UEGT10125 | Sitapur | CIVIL (1.2X1.2) | Pawan Kumar Mishra | 9956493163
77 | 48724¦DMZ01 | 10.07.2018 | 48724 |  | DMZ01 | Rahul Gupta | UEGT13021 | Sitapur | CIVIL (1.2X1.2) | Awatar Singh | 9984496285
78 | 48724¦KNSH09 | 10.07.2018 | 48724 |  | KNSH09 | Rahul Gupta | UEGT10447 | Shahjahanpur | CIVIL (1.2X1.2) | OM Prakash Singh | 9919901002
79 | 48724¦BRM01 | 10.07.2018 | 48724 |  | BRM01 | Rahul Gupta | UEGT12356 | Sitapur | CIVIL (1.2X1.2) | Pawan Kumar Mishra | 9956493163
80 | 48724¦AUB01 | 10.07.2018 | 48724 |  | AUB01 | Rahul Gupta | UEGT11095 | Sitapur | CIVIL (1.2X1.2) | Amit Kumar Mishra | 9648474341
81 | 48705¦CHP01 | 10.07.2018 | 48705 |  | CHP01 | Rahul Gupta | UEGT12226 | Sitapur | EW,MWIP55 | Vivek Singh | 9648010660
82 | 48705¦CKR01 | 10.07.2018 | 48705 |  | CKR01 | Rahul Gupta | UEGT10364 | Lakhimpur | 3 EPM,EW & MW IP55 | Ravi Prakash Singh | 9919390300
83 | 48705¦KPT01 | 10.07.2018 | 48705 |  | KPT01 | Rahul Gupta | UEGT12670 | Lakhimpur | EW,MWIP55 | Sunil Kumar Gupta | 9984999462
84 | 48705¦LKHD06 | 10.07.2018 | 48705 |  | LKHD06 | Rahul Gupta | UEGT10272 | Shahjahanpur | 3 EPM,EW & MW IP55 | OM Prakash Singh | 9919901002
85 | 48705¦SJK01 | 10.07.2018 | 48705 |  | SJK01 | Rahul Gupta | UEGT13076 | Lakhimpur | 3 EPM,EW & MW IP55 | Sunil Kumar Gupta | 9984999462
86 | 48705¦MEY01 | 10.07.2018 | 48705 |  | MEY01 | Rahul Gupta | UEGT12327 | Lakhimpur | 3 EPM,EW & MW IP55 | Upendra Kumar Dixit | 9839212570
87 | 48705¦RMA01 | 10.07.2018 | 48705 |  | RMA01 | Rahul Gupta | UEGT12383 | Lakhimpur | 3 EPM,EW & MW IP55 | Mukesh Kumar Mishra | 8052056483
88 | 48705¦BUW01 | 10.07.2018 | 48705 |  | BUW01 | Rahul Gupta | UEGT11940 | Lakhimpur | 3 EPM,EW & MW IP55 | Mukesh Kumar Mishra | 8052056483
89 | 48705¦KYS01 | 10.07.2018 | 48705 |  | KYS01 | Rahul Gupta | UEGT12702 | Lakhimpur | EW,MWIP55 | Mohd. Shahid Khan | 7081990896
90 | 48705¦LDH01 | 10.07.2018 | 48705 |  | LDH01 | Rahul Gupta | UEGT11659 | Lakhimpur | 3 EPM,EW & MW IP55 | Upendra Kumar Dixit | 9839212570
91 | 48705¦AID01 | 10.07.2018 | 48705 |  | AID01 | Rahul Gupta | UEGT12582 | Lakhimpur | 3 EPM,EW & MW IP55 | Shakeel Mirza | 8009937140
92 | 48705¦SKV01 | 10.07.2018 | 48705 |  | SKV01 | Rahul Gupta | UEGT12069 | Lakhimpur | 3 EPM,EW & MW IP55 | Santosh Kumar Singh | 9838357222
93 | 48705¦UDK01 | 10.07.2018 | 48705 |  | UDK01 | Rahul Gupta | UEGT12110 | Sitapur | 3 EPM,EW & MW IP55 | Surya Prakash Singh | 9956901615
94 | 48705¦ABY01 | 10.07.2018 | 48705 |  | ABY01 | Rahul Gupta | UEGT12196 | Lakhimpur | 3 EPM,EW & MW IP55 | Shakeel Mirza | 8009937140
95 | 48705¦GBT01 | 10.07.2018 | 48705 |  | GBT01 | Rahul Gupta | UEGT12614 | Lakhimpur | 3 EPM,EW & MW IP55 | Ravi Prakash Singh | 9919390300
96 | 48705¦SWR01 | 10.07.2018 | 48705 |  | SWR01 | Rahul Gupta | UEGT11732 | Lakhimpur | 3 EPM,EW & MW IP55 | Shakeel Mirza | 8009937140
97 | 48705¦STSH03 | 10.07.2018 | 48705 |  | STSH03 | Rahul Gupta | UEGT10561 | Lakhimpur | 3 EPM,EW & MW IP55 | Santosh Kumar Singh | 9838357222