## Sheet1
Project | Indus ID | Ref. no. | Site Name | Allocation Date | Survey PO | Survey WCC | PO Number | PO Status | NEW PO | PO Status | PO Date | PO Amount | Total KG | Pedastal require/not | site address | Dist. | Tower Type | Tech. | FSE | CM | Vendor | Status | Audit staus | Audit date | PPS | Remarks | WCC
PS | IN-1012333 | R/RL-2726681 | SUR144 | April |  |  | 14030131040 | Finally Closed | 14030181982 | Finally Closed | 2020-08-07 | 33872.26 | 204.91 | NR | Ishwarkrupa Complex, 348-chhapaniya Maholla, Adajan Gam, Surat | Surat | RTP | Sandip Rohit/7575807006 | Nilesh Mahajan/8238022930 | Kishor Baviskar/9727729650 | jagdish bhai | HOLD | NR |  |  | Survey done_11-03-2021, 1 gsm need to dismantle,40 TO 50 kg material only load on site | NR
PS | IN-1003818 | R/RL-2050409 | SRTrandvilD | April |  |  | 14030131024 | Finally Closed | 14030180567 | Closed | 2020-07-27 | 52838.86 | 347.196 |  | Royal Appartment, Vakharwadi Rander. Surat. | Surat | RTP | Bharat Patel/8511187364 | Nilesh Mahajan/8238022930 | Kishor Baviskar/9727729650 | shree | Done | FA | 2020-07-17 |  | Bill done | 1418201508
PS | IN-1041582 | R/RL-2764077 | ESURRAJRESID1 | April |  |  | 14030131041 | Finally Closed | 14030181983 | Finally Closed | 2020-08-07 | 61625.31 | 365.37 | 6 Pedastal | Green Vally Apt. Bolck-c, Behind Sahaj Super Store, Surat | Surat | RTP | Amit Oza/8511187920 | Nilesh Mahajan/8238022930 | Kishor Baviskar/9727729650 | jagdish bhai | HOLD | NR |  |  | Drilling Issue confirm with FSE_26-08-2021 | NR