## Sheet1
PO Number | Line | Site ID | Project Name | Item/Job | Description | UOM | Qty | Price | Amount | Task Name | C1 | C2 | C3 | E1 | C4 | Qty Total | Total
14030263684 | 74 | IN-3159009 | R/NN-693798 | 25-1B0000-0-00-ZZ-ZZ-477 | Supply and filling with fine/Yamuna sand in plinth under the floors in a layer of 15-20cms including watering, ramming, consolidating and dressing complete. | CUBIC METER | 1.476 | 233 | 343.91 | Civil Work |  |  | 1.476 |  |  | 1.476 | 343.908
14030263684 | 13 | IN-3159009 | R/NN-693798 | 24-600000-0-00-ZZ-ZZ-102 | Fixing & Levelling of Foundation Bolt & Tower Template | Each | 1 | 3180 | 3180 | Civil Work |  | 1 |  |  |  | 1 | 3180
14030263684 | 36 | IN-3159009 | R/NN-693798 | 22-435000-0-00-ZZ-ZZ-654 | Earthing,GI strip (25x3) mm with all installation accessories,(As per Indus Standards and Guidelines) | Meter | 110 | 90 | 9900 | Civil Work |  |  |  | 119.5 |  | 119.5 | 10755
14030263684 | 6 | IN-3159009 | R/NN-693798 | 12-422000-0-01-ZZ-ZZ-000 | Earthing, EGB GI Busbar, 300x150x6 with all installation accessories, Version 1.0 | Meter | 2 | 398 | 796 | Other Services &Lots |  |  |  | 2 |  | 2 | 796
14030263684 | 48 | IN-3159009 | R/NN-693798 | 12-154067-0-00-ZZ-ZZ-000 | ELCB,63A,4 Pole,30 mA | Each | 1 | 1397 | 1397 | Other Matl. (Serial) |  |  |  | 1 |  | 1 | 1397
14030263684 | 26 | IN-3159009 | R/NN-693798 | 24-600000-0-00-ZZ-ZZ-604 | Door & Window Fitting Charges - Lock 7-liver (link,plaza,harison make) | Each | 3 | 265 | 795 | Civil Work |  |  |  | 6 | 5 | 11 | 2915
14030263684 | 47 | IN-3159009 | R/NN-693798 | 12-C00000-C-00-ZZ-ZZ-162 | Conduit/Pipe - PVC 40 mm - Capex | Meter | 30 | 58 | 1740 | Electrical Work |  |  |  | 5.5 |  | 5.5 | 319
14030263684 | 45 | IN-3159009 | R/NN-693798 | 12-C00000-0-01-ZZ-ZZ-012 | Conduit - PVC 32 mm Flexible (ISI Mark),Version 1.0 | Meter | 30 | 48 | 1440 | Electrical Work |  |  |  | 20 |  | 20 | 960
14030263684 | 50 | IN-3159009 | R/NN-693798 | 22-211AP0-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,25 Sq MM,4 Core,Aluminum Armoured, HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 15 | 211 | 3165 | Civil Work |  |  |  | 12 |  | 12 | 2532
14030263684 | 54 | IN-3159009 | R/NN-693798 | 22-205930-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,2.5 Sq MM,3 Core,Copper Armoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 5 | 138 | 690 | Civil Work |  |  |  | 9.5 |  | 9.5 | 1311
14030263684 | 51 | IN-3159009 | R/NN-693798 | 22-205830-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,2.5 Sq MM,2 Core,Copper Armoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 15 | 111 | 1665 | Civil Work |  |  |  | 5 |  | 5 | 555
14030263684 | 53 | IN-3159009 | R/NN-693798 | 22-210830-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,16 Sq MM,2 Core,Copper Armoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 15 | 416 | 6240 | Civil Work |  |  |  | 9 |  | 9 | 3744
14030263684 | 52 | IN-3159009 | R/NN-693798 | 22-210560-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,16 Sq MM,1 Core Green,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 15 | 163 | 2445 | Civil Work |  |  |  | 10 |  | 10 | 1630
14030263684 | 11 | IN-3159009 | R/NN-693798 | 25-210000-0-00-ZZ-ZZ-262 | Brick work with bricks class designation-105, in foundation up to DPC level in mortar mix 1:4(1 cement: 6-coarse sand) including all materials, labour, tools & plants etc. required for proper completion of work with minimum 6-days curing. | CUBIC METER | 3.164 | 4800 | 15187.2 | Civil Work |  |  | 1.47 |  |  | 1.47 | 7056
14030263684 | 34 | IN-3159009 | R/NN-693798 | 2A-600000-C-00-ZZ-ZZ-168 | Alarm termination Charges - Capex | Each | 1 | 1000 | 1000 | Electrical Work |  |  |  | 1 |  | 1 | 1000
14030263684 | 49 | IN-3159009 | R/NN-693798 | 12-900000-0-01-ZZ-ZZ-020 | 5/15 Amps Switch & Socket Assembly - OD Type,Version 1.0 | Each | 1 | 460 | 460 | Electrical Work |  |  |  | 1 |  | 1 | 460
14030263684 | 25 | IN-3159009 | R/NN-693798 | 12-900000-0-01-ZZ-ZZ-026 | Krone BOX, 10 PAIR, Indoor,Version 1.0 | Each | 1 | 242 | 242 | Electrical Work |  |  |  | 1 |  | 1 | 242
14030263684 | 9 | IN-3159009 | R/NN-693798 | 28-600000-C-00-ZZ-ZZ-001 | Installation,Signage Board - Capex | Each | 1 | 50 | 50 | Other Services &Lots |  |  |  | 1 |  | 1 | 50
14030263684 | 31 | IN-3159009 | R/NN-693798 | 24-200000-0-00-ZZ-ZZ-147 | Installation,CABLE TRAY | Each | 1 | 200 | 200 | Civil Work |  |  |  | 34 |  | 34 | 6800
14030263684 | 28 | IN-3159009 | R/NN-693798 | 24-500000-0-00-ZZ-ZZ-704 | Installation, Grouting, Earthing and Commissioning of OD BB Cabinet,(As per Indus Standards and Guidelines) | Each | 1 | 1500 | 1500 | Battery |  |  |  | 1 |  | 1 | 1500
14030263684 | 57 | IN-3159009 | R/NN-693798 | 22-214760-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,70 Sq MM,1 Core Red,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 4 | 737 | 2948 | Civil Work |  |  |  | 4.5 |  | 4.5 | 3316.5
14030263684 | 56 | IN-3159009 | R/NN-693798 | 22-214660-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,70 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 4 | 737 | 2948 | Civil Work |  |  |  | 4.5 |  | 4.5 | 3316.5
14030263684 | 23 | IN-3159009 | R/NN-693798 | 22-212AP0-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,35 Sq MM,4 Core,Aluminum Armoured, HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | Meter | 10 | 269 | 2690 | Civil Work |  |  |  | 9 |  | 9 | 2421
14030263684 | 30 | IN-3159009 | R/NN-693798 | 21-390000-0-00-ZZ-ZZ-712 | Installation, Grouting, Earthing Commisioning testing of Power Panel -SP including end termination of power cables using glands and lugs including coordination with Panel OEM,(As per Indus Standards and Guidelines) | Each | 1 | 1000 | 1000 | Other Services &Lots |  |  |  | 1 |  | 1 | 1000
14030263684 | 19 | IN-3159009 | R/NN-693798 | 21-D00000-0-00-ZZ-ZZ-705 | Installation, Grouting, Earthing & Commissioning & OD TX Rack,(As per Indus Standards and Guidelines) | Each | 1 | 200 | 200 | Tx Rack |  |  |  | 1 |  | 1 | 200
14030263684 | 33 | IN-3159009 | R/NN-693798 | 21-320400-0-00-ZZ-ZZ-064 | Installation, DCDB, 8 way, (Indoor/Outdoor) installation charges including laying of cables and all accessories (bolts used for DCDB, cable ties etc.) | Each | 1 | 1000 | 1000 | Other Services &Lots |  |  |  | 1 |  | 1 | 1000
14030263684 | 16 | IN-3159009 | R/NN-693798 | 21-600000-0-00-ZZ-ZZ-706 | Installation, Commissioning & Testing of SMPS,(As per Indus Standards and Guidelines) | Each | 1 | 1200 | 1200 | SMPS |  |  |  | 1 |  | 1 | 1200
14030263684 | 14 | IN-3159009 | R/NN-693798 | 22-600000-0-00-ZZ-ZZ-848 | Installation and Commisioning of SPD Box including end termination of cables (As per Indus Standards and Guidelines) | Each | 1 | 500 | 500 | Tower |  |  |  | 1 |  | 1 | 500
14030263684 | 73 | IN-3159009 | R/NN-693798 | 22-440000-0-00-ZZ-ZZ-169 | Installation & Commissioning,Maintenance Free Chemical Earthing | Each | 2 | 2000 | 4000 | Civil Work |  |  | 2 |  |  | 2 | 4000
14030263684 | 41 | IN-3159009 | R/NN-693798 | 12-111026-0-00-ZZ-ZZ-000 | MCB,40A,1 Pole,C Curve | Each | 1 | 143 | 143 | Other Matl. (Serial) |  |  |  | 1 |  | 1 | 143
14030263684 | 55 | IN-3159009 | R/NN-693798 | 22-201250-0-03-ZZ-ZZ-000 | Supply & Laying of Cable,0.5 MM Dia,5 Pair,Annealed Tinned Copper single strand Unarmoured(FRLS), Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories | Meter | 25 | 20 | 500 | Civil Work |  |  |  | 15.5 |  | 15.5 | 310
14030263684 | 5 | IN-3159009 | R/NN-693798 | 22-610000-0-00-ZZ-ZZ-469 | Supply & Installation Charges,Lightening Arrestor,Lightening Protection | Each | 1 | 1600 | 1600 | Tower |  |  |  | 1 |  | 1 | 1600
14030263684 | 69 | IN-3159009 | R/NN-693798 | 2D-300000-C-00-ZZ-ZZ-663 | Shuttering for GBT / GBM Sites - MS Sheet / Plywood (As per Indus Standards and Guidelines) - Capex | Sq. Meter | 76.284 | 210 | 16019.64 | Civil Work | 21.84 | 10.8 | 33.131 |  |  | 65.771 | 13811.91
14030263684 | 77 | IN-3159009 | R/NN-693798 | 25-100000-0-00-ZZ-ZZ-722 | Plain Cement Concrete - M10 grade (1:3:6),(As per Indus Standards and Guidelines) | CUBIC METER | 6.984 | 4715 | 32929.56 | Civil Work | 1.4 |  | 3.497 |  | 1.008 | 5.905 | 27842.075
14030263684 | 18 | IN-3159009 | R/NN-693798 | 12-C00000-0-01-ZZ-ZZ-136 | PLB HDPE Pipe - OD 40mm, 3.5mm Thk (For OFC Duct),Version 1.0 | Meter | 70 | 94 | 6580 | Electrical Work |  |  |  | 1.5 |  | 1.5 | 141
14030263684 | 65 | IN-3159009 | R/NN-693798 | 24-900000-C-00-ZZ-ZZ-F08 | Mount Installation Charges per mount (for 1st mount per site, Only 1 quantity allowed) - Capex | Each | 1 | 1500 | 1500 | Tower |  |  |  | 1 |  | 1 | 1500
14030263684 | 32 | IN-3159009 | R/NN-693798 | 25-100000-0-00-ZZ-ZZ-742 | Mechanical anchoring for M16 anchor bolt,(As per Indus Standards and Guidelines) | Each | 20 | 53 | 1060 | Civil Work |  |  |  | 15 |  | 15 | 795
14030263684 | 38 | IN-3159009 | R/NN-693798 | 12-1242E9-C-00-ZZ-ZZ-000 | MCCB,100A,4 Pole,25KA,Magnetic Thermal Release Including Spreader Links,compliant with IS 13947(Part 2):1993/ IEC-60947-2, Capex | Each | 1 | 2365 | 2365 | Other Matl. (Serial) |  |  |  | 1 |  | 1 | 2365
14030263684 | 44 | IN-3159009 | R/NN-693798 | 12-120000-0-00-ZZ-ZZ-001 | MCCB Box | Each | 3 | 880 | 2640 | Other Matl. (Serial) |  |  |  | 1 |  | 1 | 880
14030263684 | 72 | IN-3159009 | R/NN-693798 | 15-100000-0-00-ZZ-ZZ-847 | Reinforcement Steel - Tor steel HYSD Fe- 500 grade,(As per Indus Standards and Guidelines), ISI marked and approved make ( circle specific make ) including cutting, bending & laying ,Including binding wires etc complete | Kilogram | 2398.024 | 70.75 | 169660.2 | Civil Work | 1227.7 |  | 666.16 |  |  | 1893.86 | 133990.595
14030263684 | 71 | IN-3159009 | R/NN-693798 | 2D-100000-0-02-ZZ-ZZ-832 | Reinforced Cement Concrete - M 20 grade (1:1.5:3) for Ground Based Sites, Version 1.1, excluding reinforcement steel (As per Indus Standards and Guidelines) | CUBIC METER | 23.428 | 6645 | 155679.06 | Civil Work |  |  | 7.399 |  |  | 7.399 | 49166.355
14030263548 | 1 | IN-3159009 | R/NN-693798 | 22-300000-C-00-ZZ-ZZ-A17 | Installation charges of Meter Box - Capex | Each | 1 | 4770 | 4770 | EB Cost |  |  |  | 1 |  | 1 | 4770
14030263548 | 3 | IN-3159009 | R/NN-693798 | 12-900000-0-01-ZZ-ZZ-024 | Mounting Frame for EB Meter Box,Version 1.0 | Each | 2 | 530 | 1060 | Electrical Work |  |  |  | 1 |  | 1 | 530
14030263548 | 2 | IN-3159009 | R/NN-693798 | 2B-300000-0-00-ZZ-ZZ-473 | Supply of EB Material for Line Erection - Installation | Each | 1 | 6250 | 6250 | EB Cost |  |  |  | 1 |  | 1 | 6250