## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
4 |  | 1 | Installation, DCDB, 8 way, (Indoor/Outdoor) installation charges including laying of cables and all accessories (bolts used for DCDB, cable ties etc.) | 2022-09-30 | Each | 1000 | 1 | 0 | 1 |  | 1000 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
6 |  | 1 | Installation, Grouting, Earthing & Commissioning & OD TX Rack,(As per Indus Standards and Guidelines) | 2022-09-30 | Each | 200 | 1 | 0 | 1 |  | 200 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
7 |  | 1 | MCB,32A,1 Pole,C Curve | 2022-09-30 | Each | 80 | 1 | 0 | 1 |  | 80 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
9 |  | 1 | Mount Installation Charges per mount (For >=2 mount per site only, not applicable for 1st mount installation) - Capex | 2022-09-30 | Each | 1000 | 3 | 0 | 3 |  | 3000 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
10 |  | 1 | Mount Installation Charges per mount (for 1st mount per site, Only 1 quantity allowed) - Capex | 2022-09-30 | Each | 1500 | 1 | 0 | 1 |  | 1500 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
11 |  | 1 | Project Management Charges for Upgradation of Only Class B/C Material without outage on Existing Sites | 2022-09-30 | Each | 1250 | 1 | 0 | 1 |  | 1250 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
14 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-09-30 | Meter | 387.24 | 15 | 0 | 1.67 |  | 646.6908 | 5161.9092 | 11.13 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
15 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Red,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-09-30 | Meter | 387.24 | 15 | 0 | 1.3 |  | 503.412 | 5305.188 | 8.67 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital
16 |  | 1 | Transportation from Indus WH to site for Minor upgrade site including unloading of material at site | 2022-09-30 | Each | 1140 | 3.9474 | 0 | 3.9474 |  | 4500 | 0 | 100 | APPROVED |  | IN-3001385 | R/RES-512345 | Narayan Hospital