## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
3 |  | 1 | Installation, DCDB, 8 way, (Indoor/Outdoor) installation charges including laying of cables and all accessories (bolts used for DCDB, cable ties etc.) | 2022-10-31 | Each | 1000 | 1 | 0 | 1 |  | 1000 | 0 | 100 | APPROVED |  | IN-1040695 | R/RES-512971 | NJTPJETPURPAV1
6 |  | 1 | Project Management Charges for Upgradation of Only Class B/C Material without outage on Existing Sites | 2022-10-31 | Each | 1250 | 1 | 0 | 1 |  | 1250 | 0 | 100 | APPROVED |  | IN-1040695 | R/RES-512971 | NJTPJETPURPAV1
8 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-10-31 | Meter | 360 | 4.1667 | 0 | 4.1667 |  | 1500.0001 | 0 | 100 | APPROVED |  | IN-1040695 | R/RES-512971 | NJTPJETPURPAV1
10 |  | 1 | Transportation from Indus WH to site for Minor upgrade site including unloading of material at site | 2022-10-31 | Each | 1990 | 3.0151 | 0 | 3.0151 |  | 5999.9992 | 0 | 100 | APPROVED |  | IN-1040695 | R/RES-512971 | NJTPJETPURPAV1