## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
4 |  | 1 | Mount Installation Charges per mount (For >=2 mount per site only, not applicable for 1st mount installation) - Capex | 2022-10-31 | Each | 1000 | 5 | 0 | 5 |  | 5000 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663
6 |  | 1 | Project Management Charges for Upgradation of Only Class B/C Material without outage on Existing Sites | 2022-10-31 | Each | 1250 | 1 | 0 | 1 |  | 1250 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663
8 |  | 1 | Earthing,GI strip (25x3) mm with all installation accessories,(As per Indus Standards and Guidelines) | 2022-10-31 | Meter | 90 | 5 | 0 | 5 |  | 450 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663
10 |  | 1 | Installation, DCDB, 8 way, (Indoor/Outdoor) installation charges including laying of cables and all accessories (bolts used for DCDB, cable ties etc.) | 2022-10-31 | Each | 1000 | 1 | 0 | 1 |  | 1000 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663
12 |  | 1 | Installation, Grouting, Earthing & Commissioning & OD TX Rack,(As per Indus Standards and Guidelines) | 2022-10-31 | Each | 200 | 1 | 0 | 1 |  | 200 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663
19 |  | 1 | Transportation from Indus WH to site for Minor upgrade site including unloading of material at site | 2022-10-31 | Each | 1140 | 3.2143 | 0 | 3.2143 |  | 3664.286 | 0 | 100 | APPROVED |  | IN-3127835 | R/RES-513300 | Relocation of GT4663