## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
3 |  | 1 | MCB,32A,1 Pole,C Curve | 2022-12-31 | Each | 80 | 1 | 0 | 1 |  | 80 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
4 |  | 1 | MCB,63A,1 Pole,10KA,C Curve compliant with IS 13947(Part 2):1993/ IEC-60947-2 | 2022-12-31 | Each | 152 | 1 | 0 | 1 |  | 152 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
5 |  | 1 | Mount Installation Charges per mount (For >=2 mount per site only, not applicable for 1st mount installation) - Capex | 2022-12-31 | Each | 1000 | 5 | 0 | 5 |  | 5000 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
7 |  | 1 | Project Management Charges for Upgradation of Only Class B/C Material without outage on Existing Sites | 2022-12-31 | Each | 1250 | 1 | 0 | 1 |  | 1250 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
9 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-12-31 | Meter | 360 | 4 | 0 | 4 |  | 1440 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
10 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Red,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-12-31 | Meter | 360 | 4 | 0 | 4 |  | 1440 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1
11 |  | 1 | Transportation from Indus WH to site for Minor upgrade site including unloading of material at site | 2022-12-31 | Each | 1990 | 1 | 0 | 1 |  | 1990 | 0 | 100 | APPROVED |  | IN-1039771 | R/RL-5676998 | NASTASHTAGAM1