## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
3 |  | 1 | MCB,63A,1 Pole,10KA,C Curve compliant with IS 13947(Part 2):1993/ IEC-60947-2 | 2022-11-30 | Each | 152 | 2 | 0 | 2 |  | 304 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
4 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 360 | 4.5 | 0 | 4.5 |  | 1620 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
8 |  | 1 | Installation and Commisioning of SPD Box including end termination of cables (As per Indus Standards and Guidelines) | 2022-11-30 | Each | 500 | 1 | 0 | 1 |  | 500 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
9 |  | 1 | Installation Charges for PMS - PIU/PMS | 2022-11-30 | Each | 2500 | 1 | 0 | 1 |  | 2500 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
10 |  | 1 | Mechanical anchoring for M12 anchor bolt,(As per Indus Standards and Guidelines) | 2022-11-30 | Each | 53 | 4 | 0 | 4 |  | 212 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
11 |  | 1 | Project Management Charges for Upgradation of Single Class A (Including Class B/C) material on Existing Sites | 2022-11-30 | Each | 5000 | 1 | 0 | 1 |  | 5000 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
12 |  | 1 | Transportation from Indus WH to site for Major upgrade site including unloading of material at Ground floor of site | 2022-11-30 | Each | 11650 | 2 | 0 | 2 |  | 23300 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town
14 |  | 1 | Supply & Laying of Cable,16 Sq MM,1 Core Green,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 163 | 4 | 0 | 4 |  | 652 | 0 | 100 | APPROVED |  | IN-1291300 | R/RL-5677282 | Vapi town