## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
4 |  | 1 | MCB,63A,1 Pole,10KA,C Curve compliant with IS 13947(Part 2):1993/ IEC-60947-2 | 2022-11-30 | Each | 152 | 2 | 0 | 2 |  | 304 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
5 |  | 1 | Mount Installation Charges per mount (For >=2 mount per site only, not applicable for 1st mount installation) - Capex | 2022-11-30 | Each | 1000 | 5 | 0 | 4 |  | 4000 | 1000 | 80 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
6 |  | 1 | Mount Installation Charges per mount (for 1st mount per site, Only 1 quantity allowed) - Capex | 2022-11-30 | Each | 1500 | 1 | 0 | 1 |  | 1500 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
7 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 360 | 9.2 | 0 | 9.2 |  | 3312 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
9 |  | 1 | Earthing,GI strip (25x3) mm with all installation accessories,(As per Indus Standards and Guidelines) | 2022-11-30 | Meter | 90 | 11 | 0 | 11 |  | 990 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
12 |  | 1 | Installation Charges for PMS - PIU/PMS | 2022-11-30 | Each | 2500 | 1 | 0 | 1 |  | 2500 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
13 |  | 1 | Mechanical anchoring for M12 anchor bolt,(As per Indus Standards and Guidelines) | 2022-11-30 | Each | 53 | 4 | 0 | 4 |  | 212 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
14 |  | 1 | Project Management Charges for Upgradation of Single Class A (Including Class B/C) material on Existing Sites | 2022-11-30 | Each | 5000 | 1 | 0 | 1 |  | 5000 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
15 |  | 1 | Transportation from Indus WH to site for Major upgrade site including unloading of material at Ground floor of site | 2022-11-30 | Each | 11650 | 1 | 0 | 1 |  | 11650 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
16 |  | 1 | Supply & Laying of Cable,6 Sq MM,2 Core,Copper Armoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 198 | 8 | 0 | 4.5 |  | 891 | 693 | 56.25 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
17 |  | 1 | Supply & Laying of Cable,16 Sq MM,1 Core Green,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 163 | 4 | 0 | 3.2 |  | 521.6 | 130.4 | 80 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD
18 |  | 1 | Supply & Laying of Cable,25 Sq MM,4 Core,Aluminum Armoured, HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 211 | 16.5 | 0 | 16.5 |  | 3481.5 | 0 | 100 | APPROVED |  | IN-1110223 | R/RL-5685545 | CHHIRI ROAD