## Sheet1
Line | Line | Pay Item | Description | Need-By Date | UOM | Price | Ordered | Previously Requested/Delivered | Requested/Delivered | Material Stored | Amount | Balance Remaining | Progress (%) | Status | Comments | Site ID | Project ID | Site Name
1 |  | 1 | Installation Charges for PMS - PIU/PMS | 2022-11-30 | Each | 2500 | 1 | 0 | 1 |  | 2500 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
2 |  | 1 | Mechanical anchoring for M12 anchor bolt,(As per Indus Standards and Guidelines) | 2022-11-30 | Each | 53 | 4 | 0 | 4 |  | 212 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
6 |  | 1 | MCB,63A,1 Pole,10KA,C Curve compliant with IS 13947(Part 2):1993/ IEC-60947-2 | 2022-11-30 | Each | 152 | 2 | 0 | 2 |  | 304 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
7 |  | 1 | Mount Installation Charges per mount (For >=2 mount per site only, not applicable for 1st mount installation) - Capex | 2022-11-30 | Each | 1000 | 3 | 0 | 2 |  | 2000 | 1000 | 66.67 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
8 |  | 1 | Mount Installation Charges per mount (for 1st mount per site, Only 1 quantity allowed) - Capex | 2022-11-30 | Each | 1500 | 1 | 0 | 1 |  | 1500 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
9 |  | 1 | Supply & Laying of Cable,35 Sq MM,1 Core Black,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 360 | 19.5 | 0 | 19.5 |  | 7020 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
11 |  | 1 | Earthing,GI strip (25x3) mm with all installation accessories,(As per Indus Standards and Guidelines) | 2022-11-30 | Meter | 90 | 6 | 0 | 6 |  | 540 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
14 |  | 1 | Project Management Charges for Upgradation of Single Class A (Including Class B/C) material on Existing Sites | 2022-11-30 | Each | 5000 | 1 | 0 | 1 |  | 5000 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
15 |  | 1 | Transportation from Indus WH to site for Major upgrade site including unloading of material at Ground floor of site | 2022-11-30 | Each | 11650 | 2 | 0 | 2 |  | 23300 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
16 |  | 1 | Supply & Laying of Cable,6 Sq MM,2 Core,Copper Armoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 198 | 43.5 | 0 | 42 |  | 8316 | 297 | 96.55 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
17 |  | 1 | Supply & Laying of Cable,16 Sq MM,1 Core Green,Copper Unarmoured Multi strand HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 163 | 6.3 | 0 | 6.3 |  | 1026.9 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC
18 |  | 1 | Supply & Laying of Cable,25 Sq MM,4 Core,Aluminum Armoured, HRFR, Version 3.0 incldg Termination with Lugs, Saddles, Cable ties, Insulation tape, Glands & other installation accessories as per Indus Standard Guidelines | 2022-11-30 | Meter | 211 | 21.5 | 0 | 21.5 |  | 4536.5 | 0 | 100 | APPROVED |  | IN-1249982 | R/RL-5687986 | VAPI GIDC